## Sheet1
| Milestone | Duration | Calculation Gideline
Launch & GRN Dates |  |  |  | Jul'25
| HIT | Calendar Month |  | WN25 - HIT 1
| GRN Week | 1st and 3rd Sunday |  | WK1 | WK2 | WK3 | WK4 | WK5
| GRN DATE | 7 days |  | 0 | 0 | 0 | 0 | 0
| Launch Sequence |  |  | Launch 1 |  | Launch 2
| LAUNCH WK | 2nd & 4th Sunday |  | WK2 | WK3 | WK4 | WK5 | WK6
| LAUNCH DATE | 7 days |  | 2025-07-10 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03
Strategy | Trend Presentation | 21 | Range Build - 21 days
| Merch Direction | 28 | Budget handover - 28 days
Vendor Week
Range Finalization | Range build | 30 | Techpack handover - 42 days
| Tech Pack Handover | 24 | Pre-Laydown - 24 days
| Planning budget handover | 7 | Pre-Laydown - 7 days
| Pre Laydown | 7 | Laydown - 7 days
| Laydown | 7 | Supplier Commitment - 7 days
| Supplier Commitment Date via Buying Notes + Briefing | 90 | Laydown + 7 days
| Distribution Handover by Planners | 14 | Laydown + 14 days
| PO Upload in OTS + Approval from Finance) | 7 | Distribution planning + 7 days
| Development Sample Approval | 60 | LSD - 60D
| PP/GPT Approval | 30 | LSD - 30D
| TOP Approval | 10 | LSD - 10D
Shipment Timelines | ADDITIONAL BUFFER | 5
| Shipment start date (Central china/ Turkey/ Cambodia) | 7 | Shipment end date - 7 days
| Shipment end date (Central china/ Turkey/ Cambodia) | 45 | RDC GRN - shipment lead time
| Shipment start date (North China) | 7 | Shipment end date - 7 days
| Shipment end date (North China) | 52 | RDC GRN - shipment lead time
| Shipment start date (Bangladesh) | 7 | Shipment end date - 7 days
| Shipment end date (Bangladesh) | 45 | RDC GRN - shipment lead time
| Shipment start date (India,Pakistan, SL) | 7 | Shipment end date - 7 days
| Shipment end date (India, Pakistan, SL) | 33 | RDC GRN - shipment lead time
| Shipment start date ( Indonesia, Vietnam, Thailand) | 7 | Shipment end date - 7 days
| Shipment end date ( Indonesia, Vietnam, Thailand) | 45 | RDC GRN - shipment lead time
| RDC GRN DATE | 7
| Launch Date | 0