## REGULAR CP_90D
REGULAR CRITICAL PATH | [11 empty] | CNY + FACTORY CLOSURE DATES 2025
EVENTS |  |  |  | EOSS - TENTATIVE (17 DEC FOR 3WK) | [8 empty] | RAMADAN DATES 2026
[8 empty] | PRE-RAMADAN LAUNCH |  | RAMADAN LAUNCHES
MONTHS |  |  | DEC'25 |  |  |  | JAN'26 |  |  |  |  | FEB'26 |  |  |  | MAR'26 |  |  |  | APR'25 |  |  |  |  | MAY'26 |  |  |  | JUN'26
HIT |  |  | SS26 - HIT 1 |  |  |  | SS26 - HIT 2 |  |  |  |  | SS26 - HIT 3 |  |  |  | SS26 - HIT 4 |  |  |  | SS26 - HIT 5 |  |  |  |  | SS26 - HIT 6 |  |  |  | SS26 - HIT 7
GRN WK Considering 7D |  |  | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52
GRN WK Considering 10D for Ramadan (Follow this for Jan /Feb / Mar)
GRN DATE |  |  | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21
Launch Sequence |  |  | 2025-11-30: Launch 1; 2025-12-14: Launch 2; 2026-01-04: Launch 1; 2026-01-18: Launch 2; 2026-02-01: Launch 1; 2026-02-15: Launch 2; 2026-03-01: Launch 1; 2026-03-15: Launch 2; 2026-03-29: Launch 1; 2026-04-12: Launch 2; 2026-05-03: Launch 1; 2026-05-17: Launch 2; 2026-05-31: Launch 1; 2026-06-14: Launch 2
Product Drop |  |  | 2025-11-30: Transition line; 2025-12-14: Transition line; 2026-01-04: Pre-Ramadan; 2026-01-18: Ramadan Drop 1; 2026-02-01: Ramadan Drop 2; 2026-02-15: Ramadan Drop 3; 2026-03-01: Ramadan Drop 4
Monthly Drop Split |  |  | 2025-11-30: 60%; 2025-12-14: 40%; 2026-01-04: 50%; 2026-01-18: 50%; 2026-02-01: 70%; 2026-02-15: 30%; 2026-03-01: 70%; 2026-03-15: 30%; 2026-03-29: 60%; 2026-04-12: 40%; 2026-05-03: 60%; 2026-05-17: 40%; 2026-05-31: 60%; 2026-06-14: 40%
LAUNCH WK |  |  | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52 | WK1
LAUNCH DATE |  |  | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28
Milestone | Duration | Calculation Guideline
Trend Presentation | 21 | Range Build - 21 days
Merch Direction | 28 | Budget handover - 28 days | 2025-12-14: 12th May - 16th May
Vendor Week
|  |  | Hit 1 Laydown |  |  |  | Hit 2 Laydown |  |  |  |  | Hit 3 Laydown |  |  |  | Hit 4 Laydown |  |  |  | Hit 5 Laydown |  |  |  |  | Hit 6 Laydown |  |  |  | Hit 7 Laydown
Range build | 30 | Techpack handover - 42 days | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-09-30 | 2025-10-07 | 2025-10-14 | 2025-10-21 | 2025-10-28
Tech Pack Handover | 24 | Pre-Laydown - 24 days | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27
Planning budget handover | 7 | Pre-Laydown - 7 days | 2025-06-22 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14
Pre Laydown | 7 | Laydown - 7 days | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-18 | 2025-10-18 | 2025-10-18 | 2025-10-18 | 2025-10-18 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21
Laydown | 7 | Supplier Commitment - 7 days | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-25 | 2025-10-25 | 2025-10-25 | 2025-10-25 | 2025-10-25 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28
Supplier Commitment Date via Buying Notes + Briefing | 90 | Laydown + 7 days | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04
Range Plan Handover to SEA Team | 7 |  | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11
Distribution Handover by Planners | 14 | Laydown + 14 days | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11
PO Upload in OTS + Approval from Finance) | 7 | Distribution planning + 7 days | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-15 | 2025-11-15 | 2025-11-15 | 2025-11-15 | 2025-11-15 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18
Development Sample Approval | 60 | LSD - 60D | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-09-30 | 2025-10-07 | 2025-10-14 | 2025-10-21 | 2025-10-28 | 2025-11-04 | 2025-11-11 | 2025-11-18 | 2025-11-25 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2026-01-06 | 2026-01-13 | 2026-01-20 | 2026-01-27 | 2026-02-03 | 2026-02-10 | 2026-02-17 | 2026-02-24 | 2026-03-03
PP/GPT Approval | 30 | LSD - 30D | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02
TOP Approval | 10 | LSD - 10D | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-29 | 2025-11-05 | 2025-11-12 | 2025-11-19 | 2025-11-26 | 2025-12-03 | 2025-12-10 | 2025-12-17 | 2025-12-24 | 2025-12-31 | 2026-01-07 | 2026-01-14 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-02-25 | 2026-03-04 | 2026-03-11 | 2026-03-18 | 2026-03-25 | 2026-04-01 | 2026-04-08 | 2026-04-15 | 2026-04-22
ADDITIONAL BUFFER | 5
Shipment start date (Central china/ Turkey/ Cambodia) | 7 | Shipment end date - 7 days | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment end date (Central china/ Turkey/ Cambodia) | 45 | RDC GRN - shipment lead time | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25 | 2026-05-02
Shipment start date (North China) | 7 | Shipment end date - 7 days | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18
Shipment end date (North China) | 52 | RDC GRN - shipment lead time | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment start date (Bangladesh) | 7 | Shipment end date - 7 days | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-08 | 2026-03-08 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment end date (Bangladesh) | 45 | RDC GRN - shipment lead time | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-15 | 2026-03-15 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25 | 2026-05-02
Shipment start date (India,Pakistan, SL) | 7 | Shipment end date - 7 days | 2025-10-09 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-09 | 2026-04-16 | 2026-04-23 | 2026-04-30 | 2026-05-07
Shipment end date (India, Pakistan, SL) | 33 | RDC GRN - shipment lead time | 2025-10-16 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-09 | 2026-04-16 | 2026-04-23 | 2026-04-30 | 2026-05-07 | 2026-05-14
Shipment start date ( Indonesia, Vietnam, Thailand, Turkey) | 7 | Shipment end date - 7 days | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment end date ( Indonesia, Vietnam, Thailand, Turkey) | 45 | RDC GRN - shipment lead time | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25 | 2026-05-02
RDC GRN DATE | 7 |  | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21
Launch Date | 0 |  | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28
Additional days for Ramadan | 3
| 215 | #VALUE! | 2025-12-07: 215; 2025-12-21: 215; 2026-01-04: 215; 2026-01-18: 215; 2026-02-08: 215; 2026-02-22: 215; 2026-03-08: 215; 2026-03-22: 215; 2026-04-05: 223; 2026-04-19: 237; 2026-05-10: 243; 2026-05-24: 243; 2026-06-07: 243; 2026-06-21: 243

## REGULAR CP_120D
REGULAR CRITICAL PATH | [11 empty] | CNY + FACTORY CLOSURE DATES 2025
EVENTS |  |  |  | EOSS - TENTATIVE (17 DEC FOR 3WK) | [8 empty] | RAMADAN DATES 2026
[8 empty] | PRE-RAMADAN LAUNCH |  | RAMADAN LAUNCHES
MONTHS |  |  | DEC'25 |  |  |  | JAN'26 |  |  |  |  | FEB'26 |  |  |  | MAR'26 |  |  |  | APR'25 |  |  |  |  | MAY'26 |  |  |  | JUN'26
HIT |  |  | SS26 - HIT 1 |  |  |  | SS26 - HIT 2 |  |  |  |  | SS26 - HIT 3 |  |  |  | SS26 - HIT 4 |  |  |  | SS26 - HIT 5 |  |  |  |  | SS26 - HIT 6 |  |  |  | SS26 - HIT 7
GRN WK Considering 7D |  |  | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52
GRN WK Considering 10D for Ramadan (Follow this for Jan /Feb / Mar)
GRN DATE |  |  | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21
Launch Sequence |  |  | 2025-11-30: Launch 1; 2025-12-14: Launch 2; 2026-01-04: Launch 1; 2026-01-18: Launch 2; 2026-02-01: Launch 1; 2026-02-15: Launch 2; 2026-03-01: Launch 1; 2026-03-15: Launch 2; 2026-03-29: Launch 1; 2026-04-12: Launch 2; 2026-05-03: Launch 1; 2026-05-17: Launch 2; 2026-05-31: Launch 1; 2026-06-14: Launch 2
Drop |  |  | 2025-11-30: Transition line; 2025-12-14: Transition line; 2026-01-04: Pre-Ramadan; 2026-01-18: Ramadan Drop 1; 2026-02-01: Ramadan Drop 2; 2026-02-15: Ramadan Drop 3; 2026-03-01: Ramadan Drop 4
Monthly Drop Split |  |  | 2025-11-30: 60%; 2025-12-14: 40%; 2026-01-04: 50%; 2026-01-18: 50%; 2026-02-01: 70%; 2026-02-15: 30%; 2026-03-01: 70%; 2026-03-15: 30%; 2026-03-29: 60%; 2026-04-12: 40%; 2026-05-03: 60%; 2026-05-17: 40%; 2026-05-31: 60%; 2026-06-14: 40%
LAUNCH WK |  |  | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52 | WK0
LAUNCH DATE |  |  | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28
Milestone | Duration | Calculation Guideline
Trend Presentation | 21 | Range Build - 21 days
Merch Direction | 28 | Budget handover - 28 days | 2025-12-14: 12th May - 16th May
Vendor Week
|  |  | Hit 1 Laydown |  |  |  | Hit 2 Laydown |  |  |  |  | Hit 3 Laydown |  |  |  | Hit 4 Laydown |  |  |  | Hit 5 Laydown |  |  |  |  | Hit 6 Laydown |  |  |  | Hit 7 Laydown
Range build | 30 | Techpack handover - 42 days | 2025-04-06 | 2025-04-13 | 2025-04-20 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-08 | 2025-06-15 | 2025-06-22 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-26 | 2025-07-26 | 2025-07-26 | 2025-07-26 | 2025-07-26 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28
Tech Pack Handover | 24 | Pre-Laydown - 24 days | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-09-30 | 2025-10-07 | 2025-10-14 | 2025-10-21 | 2025-10-28
Planning budget handover | 7 | Pre-Laydown - 7 days | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-10 | 2025-10-17 | 2025-10-24 | 2025-10-31 | 2025-11-07 | 2025-11-14
Pre Laydown | 7 | Laydown - 7 days | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05 | 2025-09-12 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-26 | 2025-10-03 | 2025-10-10 | 2025-10-17 | 2025-10-24 | 2025-10-31 | 2025-11-07 | 2025-11-14 | 2025-11-21
Laydown | 7 | Supplier Commitment - 7 days | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05 | 2025-09-12 | 2025-09-19 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-10-03 | 2025-10-10 | 2025-10-17 | 2025-10-24 | 2025-10-31 | 2025-11-07 | 2025-11-14 | 2025-11-21 | 2025-11-28
Supplier Commitment Date via Buying Notes + Briefing | 120 | Laydown + 7 days | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-10 | 2025-10-17 | 2025-10-24 | 2025-10-31 | 2025-11-07 | 2025-11-14 | 2025-11-21 | 2025-11-28 | 2025-12-05
Range Plan Handover to SEA Team | 7 |  | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-17 | 2025-10-24 | 2025-10-31 | 2025-11-07 | 2025-11-14 | 2025-11-21 | 2025-11-28 | 2025-12-05 | 2025-12-12
Distribution Handover by Planners | 14 | Laydown + 14 days | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-17 | 2025-10-24 | 2025-10-31 | 2025-11-07 | 2025-11-14 | 2025-11-21 | 2025-11-28 | 2025-12-05 | 2025-12-12
PO Upload in OTS + Approval from Finance) | 7 | Distribution planning + 7 days | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-10 | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2025-10-24 | 2025-10-31 | 2025-11-07 | 2025-11-14 | 2025-11-21 | 2025-11-28 | 2025-12-05 | 2025-12-12 | 2025-12-19
Development Sample Approval | 60 | LSD - 60D | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-09-30 | 2025-10-07 | 2025-10-14 | 2025-10-21 | 2025-10-28 | 2025-11-04 | 2025-11-11 | 2025-11-18 | 2025-11-25 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2026-01-06 | 2026-01-13 | 2026-01-20 | 2026-01-27 | 2026-02-03 | 2026-02-10 | 2026-02-17 | 2026-02-24 | 2026-03-03
PP/GPT Approval | 30 | LSD - 30D | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02
TOP Approval | 10 | LSD - 10D | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-29 | 2025-11-05 | 2025-11-12 | 2025-11-19 | 2025-11-26 | 2025-12-03 | 2025-12-10 | 2025-12-17 | 2025-12-24 | 2025-12-31 | 2026-01-07 | 2026-01-14 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-02-25 | 2026-03-04 | 2026-03-11 | 2026-03-18 | 2026-03-25 | 2026-04-01 | 2026-04-08 | 2026-04-15 | 2026-04-22
ADDITIONAL BUFFER | 5
Shipment start date (Central china/ Turkey/ Cambodia) | 7 | Shipment end date - 7 days | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment end date (Central china/ Turkey/ Cambodia) | 45 | RDC GRN - shipment lead time | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25 | 2026-05-02
Shipment start date (North China) | 7 | Shipment end date - 7 days | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18
Shipment end date (North China) | 52 | RDC GRN - shipment lead time | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment start date (Bangladesh) | 7 | Shipment end date - 7 days | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-08 | 2026-03-08 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment end date (Bangladesh) | 45 | RDC GRN - shipment lead time | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-15 | 2026-03-15 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25 | 2026-05-02
Shipment start date (India,Pakistan, SL) | 7 | Shipment end date - 7 days | 2025-10-09 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-09 | 2026-04-16 | 2026-04-23 | 2026-04-30 | 2026-05-07
Shipment end date (India, Pakistan, SL) | 33 | RDC GRN - shipment lead time | 2025-10-16 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-09 | 2026-04-16 | 2026-04-23 | 2026-04-30 | 2026-05-07 | 2026-05-14
Shipment start date ( Indonesia, Vietnam, Thailand, Turkey) | 7 | Shipment end date - 7 days | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment end date ( Indonesia, Vietnam, Thailand, Turkey) | 45 | RDC GRN - shipment lead time | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25 | 2026-05-02
RDC GRN DATE | 7 |  | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21
Launch Date | 0 |  | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28
Additional days for Ramadan | 3
| 245 | #VALUE! | 2025-12-07: 245; 2025-12-21: 245; 2026-01-04: 245; 2026-01-18: 245; 2026-02-08: 245; 2026-02-22: 245; 2026-03-08: 245; 2026-03-22: 245; 2026-04-05: 253; 2026-04-19: 267; 2026-05-10: 273; 2026-05-24: 273; 2026-06-07: 273; 2026-06-21: 273; 2026-06-28: 273

## REGULAR CP_105D
REGULAR CRITICAL PATH | [11 empty] | CNY + FACTORY CLOSURE DATES 2025
EVENTS |  |  |  | EOSS - TENTATIVE (17 DEC FOR 3WK) | [8 empty] | RAMADAN DATES 2026
[8 empty] | PRE-RAMADAN LAUNCH |  | RAMADAN LAUNCHES
MONTHS |  |  | DEC'25 |  |  |  | JAN'26 |  |  |  |  | FEB'26 |  |  |  | MAR'26 |  |  |  | APR'25 |  |  |  |  | MAY'26 |  |  |  | JUN'26
HIT |  |  | SS26 - HIT 1 |  |  |  | SS26 - HIT 2 |  |  |  |  | SS26 - HIT 3 |  |  |  | SS26 - HIT 4 |  |  |  | SS26 - HIT 5 |  |  |  |  | SS26 - HIT 6 |  |  |  | SS26 - HIT 7
GRN WK Considering 7D |  |  | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52
GRN WK Considering 10D for Ramadan (Follow this for Jan /Feb / Mar)
GRN DATE |  |  | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21
Launch Sequence |  |  | 2025-11-30: Launch 1; 2025-12-14: Launch 2; 2026-01-04: Launch 1; 2026-01-18: Launch 2; 2026-02-01: Launch 1; 2026-02-15: Launch 2; 2026-03-01: Launch 1; 2026-03-15: Launch 2; 2026-03-29: Launch 1; 2026-04-12: Launch 2; 2026-05-03: Launch 1; 2026-05-17: Launch 2; 2026-05-31: Launch 1; 2026-06-14: Launch 2
Drop |  |  | 2025-11-30: Transition line; 2025-12-14: Transition line; 2026-01-04: Pre-Ramadan; 2026-01-18: Ramadan Drop 1; 2026-02-01: Ramadan Drop 2; 2026-02-15: Ramadan Drop 3; 2026-03-01: Ramadan Drop 4
Monthly Drop Split |  |  | 2025-11-30: 60%; 2025-12-14: 40%; 2026-01-04: 50%; 2026-01-18: 50%; 2026-02-01: 70%; 2026-02-15: 30%; 2026-03-01: 70%; 2026-03-15: 30%; 2026-03-29: 60%; 2026-04-12: 40%; 2026-05-03: 60%; 2026-05-17: 40%; 2026-05-31: 60%; 2026-06-14: 40%
LAUNCH WK |  |  | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52 | WK0
LAUNCH DATE |  |  | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28
Milestone | Duration | Calculation Guideline
Trend Presentation | 21 | Range Build - 21 days
Merch Direction | 28 | Budget handover - 28 days | 2025-12-14: 12th May - 16th May
Vendor Week
|  |  | Hit 1 Laydown |  |  |  | Hit 2 Laydown |  |  |  |  | Hit 3 Laydown |  |  |  | Hit 4 Laydown |  |  |  | Hit 5 Laydown |  |  |  |  | Hit 6 Laydown |  |  |  | Hit 7 Laydown
Range build | 30 | Techpack handover - 42 days | 2025-04-21 | 2025-04-28 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04 | 2025-08-10 | 2025-08-10 | 2025-08-10 | 2025-08-10 | 2025-08-10 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13
Tech Pack Handover | 24 | Pre-Laydown - 24 days | 2025-05-21 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-29 | 2025-11-05 | 2025-11-12
Planning budget handover | 7 | Pre-Laydown - 7 days | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29
Pre Laydown | 7 | Laydown - 7 days | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06
Laydown | 7 | Supplier Commitment - 7 days | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-10 | 2025-10-10 | 2025-10-10 | 2025-10-10 | 2025-10-10 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13
Supplier Commitment Date via Buying Notes + Briefing | 105 | Laydown + 7 days | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-17 | 2025-10-17 | 2025-10-17 | 2025-10-17 | 2025-10-17 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20
Range Plan Handover to SEA Team | 7 |  | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27
Distribution Handover by Planners | 14 | Laydown + 14 days | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27
PO Upload in OTS + Approval from Finance) | 7 | Distribution planning + 7 days | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03
Development Sample Approval | 60 | LSD - 60D | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-09-30 | 2025-10-07 | 2025-10-14 | 2025-10-21 | 2025-10-28 | 2025-11-04 | 2025-11-11 | 2025-11-18 | 2025-11-25 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2026-01-06 | 2026-01-13 | 2026-01-20 | 2026-01-27 | 2026-02-03 | 2026-02-10 | 2026-02-17 | 2026-02-24 | 2026-03-03
PP/GPT Approval | 30 | LSD - 30D | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02
TOP Approval | 10 | LSD - 10D | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-29 | 2025-11-05 | 2025-11-12 | 2025-11-19 | 2025-11-26 | 2025-12-03 | 2025-12-10 | 2025-12-17 | 2025-12-24 | 2025-12-31 | 2026-01-07 | 2026-01-14 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-02-25 | 2026-03-04 | 2026-03-11 | 2026-03-18 | 2026-03-25 | 2026-04-01 | 2026-04-08 | 2026-04-15 | 2026-04-22
ADDITIONAL BUFFER | 5
Shipment start date (Central china/ Turkey/ Cambodia) | 7 | Shipment end date - 7 days | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment end date (Central china/ Turkey/ Cambodia) | 45 | RDC GRN - shipment lead time | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25 | 2026-05-02
Shipment start date (North China) | 7 | Shipment end date - 7 days | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18
Shipment end date (North China) | 52 | RDC GRN - shipment lead time | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment start date (Bangladesh) | 7 | Shipment end date - 7 days | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-08 | 2026-03-08 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment end date (Bangladesh) | 45 | RDC GRN - shipment lead time | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-15 | 2026-03-15 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25 | 2026-05-02
Shipment start date (India,Pakistan, SL) | 7 | Shipment end date - 7 days | 2025-10-09 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-09 | 2026-04-16 | 2026-04-23 | 2026-04-30 | 2026-05-07
Shipment end date (India, Pakistan, SL) | 33 | RDC GRN - shipment lead time | 2025-10-16 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-09 | 2026-04-16 | 2026-04-23 | 2026-04-30 | 2026-05-07 | 2026-05-14
Shipment start date ( Indonesia, Vietnam, Thailand, Turkey) | 7 | Shipment end date - 7 days | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment end date ( Indonesia, Vietnam, Thailand, Turkey) | 45 | RDC GRN - shipment lead time | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25 | 2026-05-02
RDC GRN DATE | 7 |  | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21
Launch Date | 0 |  | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28
Additional days for Ramadan | 3
| 230 | #VALUE! | 2025-12-07: 230; 2025-12-21: 230; 2026-01-04: 230; 2026-01-18: 230; 2026-02-08: 230; 2026-02-22: 230; 2026-03-08: 230; 2026-03-22: 230; 2026-04-05: 238; 2026-04-19: 252; 2026-05-10: 258; 2026-05-24: 258; 2026-06-07: 258; 2026-06-21: 258
[16 empty] | 162 |  |  |  | 170 |  |  |  |  | 190 |  |  |  | 190

## REGULAR CP_75D
REGULAR CRITICAL PATH | [11 empty] | CNY + FACTORY CLOSURE DATES 2025
EVENTS |  |  |  | EOSS - TENTATIVE (17 DEC FOR 3WK) | [8 empty] | RAMADAN DATES 2026
[8 empty] | PRE-RAMADAN LAUNCH |  | RAMADAN LAUNCHES
MONTHS |  |  | DEC'25 |  |  |  | JAN'26 |  |  |  |  | FEB'26 |  |  |  | MAR'26 |  |  |  | APR'25 |  |  |  |  | MAY'26 |  |  |  | JUN'26
HIT |  |  | SS26 - HIT 1 |  |  |  | SS26 - HIT 2 |  |  |  |  | SS26 - HIT 3 |  |  |  | SS26 - HIT 4 |  |  |  | SS26 - HIT 5 |  |  |  |  | SS26 - HIT 6 |  |  |  | SS26 - HIT 7
GRN WK Considering 7D |  |  | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52
GRN WK Considering 10D for Ramadan (Follow this for Jan /Feb / Mar)
GRN DATE |  |  | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21
Launch Sequence |  |  | 2025-11-30: Launch 1; 2025-12-14: Launch 2; 2026-01-04: Launch 1; 2026-01-18: Launch 2; 2026-02-01: Launch 1; 2026-02-15: Launch 2; 2026-03-01: Launch 1; 2026-03-15: Launch 2; 2026-03-29: Launch 1; 2026-04-12: Launch 2; 2026-05-03: Launch 1; 2026-05-17: Launch 2; 2026-05-31: Launch 1; 2026-06-14: Launch 2
Drop |  |  | 2025-11-30: Transition line; 2025-12-14: Transition line; 2026-01-04: Pre-Ramadan; 2026-01-18: Ramadan Drop 1; 2026-02-01: Ramadan Drop 2; 2026-02-15: Ramadan Drop 3; 2026-03-01: Ramadan Drop 4
Monthly Drop Split |  |  | 2025-11-30: 60%; 2025-12-14: 40%; 2026-01-04: 50%; 2026-01-18: 50%; 2026-02-01: 70%; 2026-02-15: 30%; 2026-03-01: 70%; 2026-03-15: 30%; 2026-03-29: 60%; 2026-04-12: 40%; 2026-05-03: 60%; 2026-05-17: 40%; 2026-05-31: 60%; 2026-06-14: 40%
LAUNCH WK |  |  | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52 | WK0
LAUNCH DATE |  |  | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28
Milestone | Duration | Calculation Guideline
Trend Presentation | 21 | Range Build - 21 days
Merch Direction | 28 | Budget handover - 28 days | 2025-12-14: 12th May - 16th May
Vendor Week
|  |  | Hit 1 Laydown |  |  |  | Hit 2 Laydown |  |  |  |  | Hit 3 Laydown |  |  |  | Hit 4 Laydown |  |  |  | Hit 5 Laydown |  |  |  |  | Hit 6 Laydown |  |  |  | Hit 7 Laydown
Range build | 30 | Techpack handover - 42 days | 2025-05-21 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-29 | 2025-11-05 | 2025-11-12
Tech Pack Handover | 24 | Pre-Laydown - 24 days | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-17 | 2025-10-24 | 2025-10-31 | 2025-11-07 | 2025-11-14 | 2025-11-21 | 2025-11-28 | 2025-12-05 | 2025-12-12
Planning budget handover | 7 | Pre-Laydown - 7 days | 2025-07-07 | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-26 | 2025-10-26 | 2025-10-26 | 2025-10-26 | 2025-10-26 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29
Pre Laydown | 7 | Laydown - 7 days | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-02 | 2025-11-02 | 2025-11-02 | 2025-11-02 | 2025-11-02 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05
Laydown | 7 | Supplier Commitment - 7 days | 2025-07-21 | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-09 | 2025-11-09 | 2025-11-09 | 2025-11-09 | 2025-11-09 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12
Supplier Commitment Date via Buying Notes + Briefing | 75 | Laydown + 7 days | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-16 | 2025-11-16 | 2025-11-16 | 2025-11-16 | 2025-11-16 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19
Range Plan Handover to SEA Team | 7 |  | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-23 | 2025-11-23 | 2025-11-23 | 2025-11-23 | 2025-11-23 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26
Distribution Handover by Planners | 14 | Laydown + 14 days | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-23 | 2025-11-23 | 2025-11-23 | 2025-11-23 | 2025-11-23 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26
PO Upload in OTS + Approval from Finance) | 7 | Distribution planning + 7 days | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-11-30 | 2025-11-30 | 2025-11-30 | 2025-11-30 | 2025-11-30 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02
Development Sample Approval | 60 | LSD - 60D | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-09-30 | 2025-10-07 | 2025-10-14 | 2025-10-21 | 2025-10-28 | 2025-11-04 | 2025-11-11 | 2025-11-18 | 2025-11-25 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2026-01-06 | 2026-01-13 | 2026-01-20 | 2026-01-27 | 2026-02-03 | 2026-02-10 | 2026-02-17 | 2026-02-24 | 2026-03-03
PP/GPT Approval | 30 | LSD - 30D | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02
TOP Approval | 10 | LSD - 10D | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-29 | 2025-11-05 | 2025-11-12 | 2025-11-19 | 2025-11-26 | 2025-12-03 | 2025-12-10 | 2025-12-17 | 2025-12-24 | 2025-12-31 | 2026-01-07 | 2026-01-14 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-02-25 | 2026-03-04 | 2026-03-11 | 2026-03-18 | 2026-03-25 | 2026-04-01 | 2026-04-08 | 2026-04-15 | 2026-04-22
ADDITIONAL BUFFER | 5
Shipment start date (Central china/ Turkey/ Cambodia) | 7 | Shipment end date - 7 days | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment end date (Central china/ Turkey/ Cambodia) | 45 | RDC GRN - shipment lead time | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25 | 2026-05-02
Shipment start date (North China) | 7 | Shipment end date - 7 days | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18
Shipment end date (North China) | 52 | RDC GRN - shipment lead time | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment start date (Bangladesh) | 7 | Shipment end date - 7 days | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-08 | 2026-03-08 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment end date (Bangladesh) | 45 | RDC GRN - shipment lead time | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-15 | 2026-03-15 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25 | 2026-05-02
Shipment start date (India,Pakistan, SL) | 7 | Shipment end date - 7 days | 2025-10-09 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-09 | 2026-04-16 | 2026-04-23 | 2026-04-30 | 2026-05-07
Shipment end date (India, Pakistan, SL) | 33 | RDC GRN - shipment lead time | 2025-10-16 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-09 | 2026-04-16 | 2026-04-23 | 2026-04-30 | 2026-05-07 | 2026-05-14
Shipment start date ( Indonesia, Vietnam, Thailand, Turkey) | 7 | Shipment end date - 7 days | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment end date ( Indonesia, Vietnam, Thailand, Turkey) | 45 | RDC GRN - shipment lead time | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25 | 2026-05-02
RDC GRN DATE | 7 |  | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21
Launch Date | 0 |  | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28
Additional days for Ramadan | 3
| 200 | #VALUE! | 2025-12-07: 200; 2025-12-21: 200; 2026-01-04: 200; 2026-01-18: 200; 2026-02-08: 200; 2026-02-22: 200; 2026-03-08: 200; 2026-03-22: 200; 2026-04-05: 208; 2026-04-19: 222; 2026-05-10: 228; 2026-05-24: 228; 2026-06-07: 228; 2026-06-21: 228

## REGULAR CP_60D
REGULAR CRITICAL PATH | [11 empty] | CNY + FACTORY CLOSURE DATES 2025
EVENTS |  |  |  | EOSS - TENTATIVE (17 DEC FOR 3WK) | [8 empty] | RAMADAN DATES 2026
[8 empty] | PRE-RAMADAN LAUNCH |  | RAMADAN LAUNCHES
MONTHS |  |  | DEC'25 |  |  |  | JAN'26 |  |  |  |  | FEB'26 |  |  |  | MAR'26 |  |  |  | APR'25 |  |  |  |  | MAY'26 |  |  |  | JUN'26
HIT |  |  | SS26 - HIT 1 |  |  |  | SS26 - HIT 2 |  |  |  |  | SS26 - HIT 3 |  |  |  | SS26 - HIT 4 |  |  |  | SS26 - HIT 5 |  |  |  |  | SS26 - HIT 6 |  |  |  | SS26 - HIT 7
GRN WK Considering 7D |  |  | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52
GRN WK Considering 10D for Ramadan (Follow this for Jan /Feb / Mar)
GRN DATE |  |  | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21
Launch Sequence |  |  | 2025-11-30: Launch 1; 2025-12-14: Launch 2; 2026-01-04: Launch 1; 2026-01-18: Launch 2; 2026-02-01: Launch 1; 2026-02-15: Launch 2; 2026-03-01: Launch 1; 2026-03-15: Launch 2; 2026-03-29: Launch 1; 2026-04-12: Launch 2; 2026-05-03: Launch 1; 2026-05-17: Launch 2; 2026-05-31: Launch 1; 2026-06-14: Launch 2
Drop |  |  | 2025-11-30: Transition line; 2025-12-14: Transition line; 2026-01-04: Pre-Ramadan; 2026-01-18: Ramadan Drop 1; 2026-02-01: Ramadan Drop 2; 2026-02-15: Ramadan Drop 3; 2026-03-01: Ramadan Drop 4
Monthly Drop Split |  |  | 2025-11-30: 60%; 2025-12-14: 40%; 2026-01-04: 50%; 2026-01-18: 50%; 2026-02-01: 70%; 2026-02-15: 30%; 2026-03-01: 70%; 2026-03-15: 30%; 2026-03-29: 60%; 2026-04-12: 40%; 2026-05-03: 60%; 2026-05-17: 40%; 2026-05-31: 60%; 2026-06-14: 40%
LAUNCH WK |  |  | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52 | WK0
LAUNCH DATE |  |  | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28
Milestone | Duration | Calculation Guideline
Trend Presentation | 21 | Range Build - 21 days
Merch Direction | 28 | Budget handover - 28 days | 2025-12-14: 12th May - 16th May
Vendor Week
|  |  | Hit 1 Laydown |  |  |  | Hit 2 Laydown |  |  |  |  | Hit 3 Laydown |  |  |  | Hit 4 Laydown |  |  |  | Hit 5 Laydown |  |  |  |  | Hit 6 Laydown |  |  |  | Hit 7 Laydown
Range build | 30 | Techpack handover - 42 days | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27
Tech Pack Handover | 24 | Pre-Laydown - 24 days | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27
Planning budget handover | 7 | Pre-Laydown - 7 days | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-09-30 | 2025-10-07 | 2025-10-14 | 2025-10-21 | 2025-10-28 | 2025-11-04 | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-18 | 2025-11-25 | 2025-12-02 | 2025-12-09 | 2025-12-16 | 2025-12-23 | 2025-12-30 | 2026-01-06 | 2026-01-13
Pre Laydown | 7 | Laydown - 7 days | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-09-30 | 2025-10-07 | 2025-10-14 | 2025-10-21 | 2025-10-28 | 2025-11-04 | 2025-11-11 | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-25 | 2025-12-02 | 2025-12-09 | 2025-12-16 | 2025-12-23 | 2025-12-30 | 2026-01-06 | 2026-01-13 | 2026-01-20
Laydown | 7 | Supplier Commitment - 7 days | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-09-30 | 2025-10-07 | 2025-10-14 | 2025-10-21 | 2025-10-28 | 2025-11-04 | 2025-11-11 | 2025-11-18 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-12-02 | 2025-12-09 | 2025-12-16 | 2025-12-23 | 2025-12-30 | 2026-01-06 | 2026-01-13 | 2026-01-20 | 2026-01-27
Supplier Commitment Date via Buying Notes + Briefing | 60 | Laydown + 7 days | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-09-30 | 2025-10-07 | 2025-10-14 | 2025-10-21 | 2025-10-28 | 2025-11-04 | 2025-11-11 | 2025-11-18 | 2025-11-25 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-09 | 2025-12-16 | 2025-12-23 | 2025-12-30 | 2026-01-06 | 2026-01-13 | 2026-01-20 | 2026-01-27 | 2026-02-03
Range Plan Handover to SEA Team | 7 |  | 2025-08-19 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-09-30 | 2025-10-07 | 2025-10-14 | 2025-10-21 | 2025-10-28 | 2025-11-04 | 2025-11-11 | 2025-11-18 | 2025-11-25 | 2025-12-02 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-16 | 2025-12-23 | 2025-12-30 | 2026-01-06 | 2026-01-13 | 2026-01-20 | 2026-01-27 | 2026-02-03 | 2026-02-10
Distribution Handover by Planners | 14 | Laydown + 14 days | 2025-08-19 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-09-30 | 2025-10-07 | 2025-10-14 | 2025-10-21 | 2025-10-28 | 2025-11-04 | 2025-11-11 | 2025-11-18 | 2025-11-25 | 2025-12-02 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-16 | 2025-12-23 | 2025-12-30 | 2026-01-06 | 2026-01-13 | 2026-01-20 | 2026-01-27 | 2026-02-03 | 2026-02-10
PO Upload in OTS + Approval from Finance) | 7 | Distribution planning + 7 days | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-09-30 | 2025-10-07 | 2025-10-14 | 2025-10-21 | 2025-10-28 | 2025-11-04 | 2025-11-11 | 2025-11-18 | 2025-11-25 | 2025-12-02 | 2025-12-09 | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-23 | 2025-12-30 | 2026-01-06 | 2026-01-13 | 2026-01-20 | 2026-01-27 | 2026-02-03 | 2026-02-10 | 2026-02-17
Development Sample Approval | 60 | LSD - 60D | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-09-30 | 2025-10-07 | 2025-10-14 | 2025-10-21 | 2025-10-28 | 2025-11-04 | 2025-11-11 | 2025-11-18 | 2025-11-25 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2026-01-06 | 2026-01-13 | 2026-01-20 | 2026-01-27 | 2026-02-03 | 2026-02-10 | 2026-02-17 | 2026-02-24 | 2026-03-03
PP/GPT Approval | 30 | LSD - 30D | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02
TOP Approval | 10 | LSD - 10D | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-29 | 2025-11-05 | 2025-11-12 | 2025-11-19 | 2025-11-26 | 2025-12-03 | 2025-12-10 | 2025-12-17 | 2025-12-24 | 2025-12-31 | 2026-01-07 | 2026-01-14 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-02-25 | 2026-03-04 | 2026-03-11 | 2026-03-18 | 2026-03-25 | 2026-04-01 | 2026-04-08 | 2026-04-15 | 2026-04-22
ADDITIONAL BUFFER | 5
Shipment start date (Central china/ Turkey/ Cambodia) | 7 | Shipment end date - 7 days | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment end date (Central china/ Turkey/ Cambodia) | 45 | RDC GRN - shipment lead time | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25 | 2026-05-02
Shipment start date (North China) | 7 | Shipment end date - 7 days | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18
Shipment end date (North China) | 52 | RDC GRN - shipment lead time | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment start date (Bangladesh) | 7 | Shipment end date - 7 days | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-08 | 2026-03-08 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment end date (Bangladesh) | 45 | RDC GRN - shipment lead time | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-15 | 2026-03-15 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25 | 2026-05-02
Shipment start date (India,Pakistan, SL) | 7 | Shipment end date - 7 days | 2025-10-09 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-09 | 2026-04-16 | 2026-04-23 | 2026-04-30 | 2026-05-07
Shipment end date (India, Pakistan, SL) | 33 | RDC GRN - shipment lead time | 2025-10-16 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-09 | 2026-04-16 | 2026-04-23 | 2026-04-30 | 2026-05-07 | 2026-05-14
Shipment start date ( Indonesia, Vietnam, Thailand, Turkey) | 7 | Shipment end date - 7 days | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment end date ( Indonesia, Vietnam, Thailand, Turkey) | 45 | RDC GRN - shipment lead time | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25 | 2026-05-02
RDC GRN DATE | 7 |  | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21
Launch Date | 0 |  | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28
Additional days for Ramadan | 3
| 185 | #VALUE! | 2025-12-07: 185; 2025-12-21: 185; 2026-01-04: 185; 2026-01-18: 185; 2026-02-08: 185; 2026-02-22: 185; 2026-03-08: 185; 2026-03-22: 185; 2026-04-05: 193; 2026-04-19: 207; 2026-05-10: 213; 2026-05-24: 213; 2026-06-07: 213; 2026-06-21: 213

## REGULAR CP_45D
REGULAR CRITICAL PATH | [11 empty] | CNY + FACTORY CLOSURE DATES 2025
EVENTS |  |  |  | EOSS - TENTATIVE (17 DEC FOR 3WK) | [8 empty] | RAMADAN DATES 2026
[8 empty] | PRE-RAMADAN LAUNCH |  | RAMADAN LAUNCHES
MONTHS |  |  | DEC'25 |  |  |  | JAN'26 |  |  |  |  | FEB'26 |  |  |  | MAR'26 |  |  |  | APR'25 |  |  |  |  | MAY'26 |  |  |  | JUN'26
HIT |  |  | SS26 - HIT 1 |  |  |  | SS26 - HIT 2 |  |  |  |  | SS26 - HIT 3 |  |  |  | SS26 - HIT 4 |  |  |  | SS26 - HIT 5 |  |  |  |  | SS26 - HIT 6 |  |  |  | SS26 - HIT 7
GRN WK Considering 7D |  |  | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52
GRN WK Considering 10D for Ramadan (Follow this for Jan /Feb / Mar)
GRN DATE |  |  | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21
Launch Sequence |  |  | 2025-11-30: Launch 1; 2025-12-14: Launch 2; 2026-01-04: Launch 1; 2026-01-18: Launch 2; 2026-02-01: Launch 1; 2026-02-15: Launch 2; 2026-03-01: Launch 1; 2026-03-15: Launch 2; 2026-03-29: Launch 1; 2026-04-12: Launch 2; 2026-05-03: Launch 1; 2026-05-17: Launch 2; 2026-05-31: Launch 1; 2026-06-14: Launch 2
Drop |  |  | 2025-11-30: Transition line; 2025-12-14: Transition line; 2026-01-04: Pre-Ramadan; 2026-01-18: Ramadan Drop 1; 2026-02-01: Ramadan Drop 2; 2026-02-15: Ramadan Drop 3; 2026-03-01: Ramadan Drop 4
Monthly Drop Split |  |  | 2025-11-30: 60%; 2025-12-14: 40%; 2026-01-04: 50%; 2026-01-18: 50%; 2026-02-01: 70%; 2026-02-15: 30%; 2026-03-01: 70%; 2026-03-15: 30%; 2026-03-29: 60%; 2026-04-12: 40%; 2026-05-03: 60%; 2026-05-17: 40%; 2026-05-31: 60%; 2026-06-14: 40%
LAUNCH WK |  |  | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52 | WK0
LAUNCH DATE |  |  | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28
Milestone | Duration | Calculation Guideline
Trend Presentation | 21 | Range Build - 21 days
Merch Direction | 28 | Budget handover - 28 days | 2025-12-14: 12th May - 16th May
Vendor Week
|  |  | Hit 1 Laydown |  |  |  | Hit 2 Laydown |  |  |  |  | Hit 3 Laydown |  |  |  | Hit 4 Laydown |  |  |  | Hit 5 Laydown |  |  |  |  | Hit 6 Laydown |  |  |  | Hit 7 Laydown
Range build | 30 | Techpack handover - 42 days | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-17 | 2025-10-24 | 2025-10-31 | 2025-11-07 | 2025-11-14 | 2025-11-21 | 2025-11-28 | 2026-01-02 | 2026-01-09
Tech Pack Handover | 24 | Pre-Laydown - 24 days | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-02-01 | 2026-02-08
Planning budget handover | 7 | Pre-Laydown - 7 days | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-29 | 2025-11-05 | 2025-11-12 | 2025-11-19 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-12-03 | 2025-12-10 | 2025-12-17 | 2025-12-24 | 2025-12-31 | 2026-01-07 | 2026-01-14 | 2026-02-18 | 2026-02-25
Pre Laydown | 7 | Laydown - 7 days | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-29 | 2025-11-05 | 2025-11-12 | 2025-11-19 | 2025-11-26 | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-10 | 2025-12-17 | 2025-12-24 | 2025-12-31 | 2026-01-07 | 2026-01-14 | 2026-01-21 | 2026-02-25 | 2026-03-04
Laydown | 7 | Supplier Commitment - 7 days | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-29 | 2025-11-05 | 2025-11-12 | 2025-11-19 | 2025-11-26 | 2025-12-03 | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-17 | 2025-12-24 | 2025-12-31 | 2026-01-07 | 2026-01-14 | 2026-01-21 | 2026-01-28 | 2026-03-04 | 2026-03-11
Supplier Commitment Date via Buying Notes + Briefing | 45 | Laydown + 7 days | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-29 | 2025-11-05 | 2025-11-12 | 2025-11-19 | 2025-11-26 | 2025-12-03 | 2025-12-10 | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-24 | 2025-12-31 | 2026-01-07 | 2026-01-14 | 2026-01-21 | 2026-01-28 | 2026-02-04 | 2026-03-11 | 2026-03-18
Range Plan Handover to SEA Team | 7 |  | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-29 | 2025-11-05 | 2025-11-12 | 2025-11-19 | 2025-11-26 | 2025-12-03 | 2025-12-10 | 2025-12-17 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-31 | 2026-01-07 | 2026-01-14 | 2026-01-21 | 2026-01-28 | 2026-02-04 | 2026-02-11 | 2026-03-18 | 2026-03-25
Distribution Handover by Planners | 14 | Laydown + 14 days | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-29 | 2025-11-05 | 2025-11-12 | 2025-11-19 | 2025-11-26 | 2025-12-03 | 2025-12-10 | 2025-12-17 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-31 | 2026-01-07 | 2026-01-14 | 2026-01-21 | 2026-01-28 | 2026-02-04 | 2026-02-11 | 2026-03-18 | 2026-03-25
PO Upload in OTS + Approval from Finance) | 7 | Distribution planning + 7 days | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-29 | 2025-11-05 | 2025-11-12 | 2025-11-19 | 2025-11-26 | 2025-12-03 | 2025-12-10 | 2025-12-17 | 2025-12-24 | 2025-12-30 | 2025-12-30 | 2025-12-30 | 2025-12-30 | 2025-12-30 | 2026-01-07 | 2026-01-14 | 2026-01-21 | 2026-01-28 | 2026-02-04 | 2026-02-11 | 2026-02-18 | 2026-03-25 | 2026-04-01
Development Sample Approval | 60 | LSD - 60D | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-09-30 | 2025-10-07 | 2025-10-14 | 2025-10-21 | 2025-10-28 | 2025-11-04 | 2025-11-11 | 2025-11-18 | 2025-11-25 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2026-01-06 | 2026-01-13 | 2026-01-20 | 2026-01-27 | 2026-02-03 | 2026-02-10 | 2026-02-17 | 2026-02-24 | 2026-03-03
PP/GPT Approval | 30 | LSD - 30D | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02
TOP Approval | 10 | LSD - 10D | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-29 | 2025-11-05 | 2025-11-12 | 2025-11-19 | 2025-11-26 | 2025-12-03 | 2025-12-10 | 2025-12-17 | 2025-12-24 | 2025-12-31 | 2026-01-07 | 2026-01-14 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-02-25 | 2026-03-04 | 2026-03-11 | 2026-03-18 | 2026-03-25 | 2026-04-01 | 2026-04-08 | 2026-04-15 | 2026-04-22
ADDITIONAL BUFFER | 5
Shipment start date (Central china/ Turkey/ Cambodia) | 7 | Shipment end date - 7 days | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment end date (Central china/ Turkey/ Cambodia) | 45 | RDC GRN - shipment lead time | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25 | 2026-05-02
Shipment start date (North China) | 7 | Shipment end date - 7 days | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18
Shipment end date (North China) | 52 | RDC GRN - shipment lead time | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment start date (Bangladesh) | 7 | Shipment end date - 7 days | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-08 | 2026-03-08 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment end date (Bangladesh) | 45 | RDC GRN - shipment lead time | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-15 | 2026-03-15 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25 | 2026-05-02
Shipment start date (India,Pakistan, SL) | 7 | Shipment end date - 7 days | 2025-10-09 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-09 | 2026-04-16 | 2026-04-23 | 2026-04-30 | 2026-05-07
Shipment end date (India, Pakistan, SL) | 33 | RDC GRN - shipment lead time | 2025-10-16 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-09 | 2026-04-16 | 2026-04-23 | 2026-04-30 | 2026-05-07 | 2026-05-14
Shipment start date ( Indonesia, Vietnam, Thailand, Turkey) | 7 | Shipment end date - 7 days | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment end date ( Indonesia, Vietnam, Thailand, Turkey) | 45 | RDC GRN - shipment lead time | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25 | 2026-05-02
RDC GRN DATE | 7 |  | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21
Launch Date | 0 |  | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28
Additional days for Ramadan | 3
| 170 | #VALUE! | 2025-12-07: 170; 2025-12-21: 170; 2026-01-04: 170; 2026-01-18: 170; 2026-02-08: 170; 2026-02-22: 170; 2026-03-08: 170; 2026-03-22: 170; 2026-04-05: 178; 2026-04-19: 192; 2026-05-10: 198; 2026-05-24: 198; 2026-06-07: 198; 2026-06-21: 170

## REGULAR CP_30D
REGULAR CRITICAL PATH | [11 empty] | CNY + FACTORY CLOSURE DATES 2025
EVENTS |  |  |  | EOSS - TENTATIVE (17 DEC FOR 3WK) | [8 empty] | RAMADAN DATES 2026
[8 empty] | PRE-RAMADAN LAUNCH |  | RAMADAN LAUNCHES
MONTHS |  |  | DEC'25 |  |  |  | JAN'26 |  |  |  |  | FEB'26 |  |  |  | MAR'26 |  |  |  | APR'25 |  |  |  |  | MAY'26 |  |  |  | JUN'26
HIT |  |  | SS26 - HIT 1 |  |  |  | SS26 - HIT 2 |  |  |  |  | SS26 - HIT 3 |  |  |  | SS26 - HIT 4 |  |  |  | SS26 - HIT 5 |  |  |  |  | SS26 - HIT 6 |  |  |  | SS26 - HIT 7
GRN WK Considering 7D |  |  | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52
GRN WK Considering 10D for Ramadan (Follow this for Jan /Feb / Mar)
GRN DATE |  |  | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21
Launch Sequence |  |  | 2025-11-30: Launch 1; 2025-12-14: Launch 2; 2026-01-04: Launch 1; 2026-01-18: Launch 2; 2026-02-01: Launch 1; 2026-02-15: Launch 2; 2026-03-01: Launch 1; 2026-03-15: Launch 2; 2026-03-29: Launch 1; 2026-04-12: Launch 2; 2026-05-03: Launch 1; 2026-05-17: Launch 2; 2026-05-31: Launch 1; 2026-06-14: Launch 2
Drop |  |  | 2025-11-30: Transition line; 2025-12-14: Transition line; 2026-01-04: Pre-Ramadan; 2026-01-18: Ramadan Drop 1; 2026-02-01: Ramadan Drop 2; 2026-02-15: Ramadan Drop 3; 2026-03-01: Ramadan Drop 4
Monthly Drop Split |  |  | 2025-11-30: 60%; 2025-12-14: 40%; 2026-01-04: 50%; 2026-01-18: 50%; 2026-02-01: 70%; 2026-02-15: 30%; 2026-03-01: 70%; 2026-03-15: 30%; 2026-03-29: 60%; 2026-04-12: 40%; 2026-05-03: 60%; 2026-05-17: 40%; 2026-05-31: 60%; 2026-06-14: 40%
LAUNCH WK |  |  | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52 | WK0
LAUNCH DATE |  |  | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28
Milestone | Duration | Calculation Guideline
Trend Presentation | 21 | Range Build - 21 days
Merch Direction | 28 | Budget handover - 28 days | 2025-12-14: 12th May - 16th May
Vendor Week
|  |  | Hit 1 Laydown |  |  |  | Hit 2 Laydown |  |  |  |  | Hit 3 Laydown |  |  |  | Hit 4 Laydown |  |  |  | Hit 5 Laydown |  |  |  |  | Hit 6 Laydown |  |  |  | Hit 7 Laydown
Range build | 30 | Techpack handover - 42 days | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24
Tech Pack Handover | 24 | Pre-Laydown - 24 days | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-23 | 2025-11-23 | 2025-11-23 | 2025-11-23 | 2025-11-23 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23
Planning budget handover | 7 | Pre-Laydown - 7 days | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12
Pre Laydown | 7 | Laydown - 7 days | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19
Laydown | 7 | Supplier Commitment - 7 days | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26
Supplier Commitment Date via Buying Notes + Briefing | 30 | Laydown + 7 days | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02
Range Plan Handover to SEA Team | 7 |  | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-09
Distribution Handover by Planners | 14 | Laydown + 14 days | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-09
PO Upload in OTS + Approval from Finance) | 7 | Distribution planning + 7 days | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-03-26 | 2026-04-02 | 2026-04-09 | 2026-04-16
Development Sample Approval | 60 | LSD - 60D | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-09-30 | 2025-10-07 | 2025-10-14 | 2025-10-21 | 2025-10-28 | 2025-11-04 | 2025-11-11 | 2025-11-18 | 2025-11-25 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2026-01-06 | 2026-01-13 | 2026-01-20 | 2026-01-27 | 2026-02-03 | 2026-02-10 | 2026-02-17 | 2026-02-24 | 2026-03-03
PP/GPT Approval | 30 | LSD - 30D | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02
TOP Approval | 10 | LSD - 10D | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-29 | 2025-11-05 | 2025-11-12 | 2025-11-19 | 2025-11-26 | 2025-12-03 | 2025-12-10 | 2025-12-17 | 2025-12-24 | 2025-12-31 | 2026-01-07 | 2026-01-14 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-02-25 | 2026-03-04 | 2026-03-11 | 2026-03-18 | 2026-03-25 | 2026-04-01 | 2026-04-08 | 2026-04-15 | 2026-04-22
ADDITIONAL BUFFER | 5
Shipment start date (Central china/ Turkey/ Cambodia) | 7 | Shipment end date - 7 days | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment end date (Central china/ Turkey/ Cambodia) | 45 | RDC GRN - shipment lead time | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25 | 2026-05-02
Shipment start date (North China) | 7 | Shipment end date - 7 days | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18
Shipment end date (North China) | 52 | RDC GRN - shipment lead time | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment start date (Bangladesh) | 7 | Shipment end date - 7 days | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-08 | 2026-03-08 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment end date (Bangladesh) | 45 | RDC GRN - shipment lead time | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-15 | 2026-03-15 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25 | 2026-05-02
Shipment start date (India,Pakistan, SL) | 7 | Shipment end date - 7 days | 2025-10-09 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-09 | 2026-04-16 | 2026-04-23 | 2026-04-30 | 2026-05-07
Shipment end date (India, Pakistan, SL) | 33 | RDC GRN - shipment lead time | 2025-10-16 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-09 | 2026-04-16 | 2026-04-23 | 2026-04-30 | 2026-05-07 | 2026-05-14
Shipment start date ( Indonesia, Vietnam, Thailand, Turkey) | 7 | Shipment end date - 7 days | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25
Shipment end date ( Indonesia, Vietnam, Thailand, Turkey) | 45 | RDC GRN - shipment lead time | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25 | 2026-05-02
RDC GRN DATE | 7 |  | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21
Launch Date | 0 |  | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28
Additional days for Ramadan | 3
| 155 | #VALUE! | 2025-12-07: 155; 2025-12-21: 155; 2026-01-04: 155; 2026-01-18: 155; 2026-02-08: 155; 2026-02-22: 155; 2026-03-08: 155; 2026-03-22: 155; 2026-04-05: 163; 2026-04-19: 177; 2026-05-10: 183; 2026-05-24: 183; 2026-06-07: 155; 2026-06-21: 155

## QR_75D
REGULAR CRITICAL PATH | [11 empty] | CNY + FACTORY CLOSURE DATES 2025
EVENTS |  |  |  | EOSS - TENTATIVE (17 DEC FOR 3WK) | [8 empty] | RAMADAN DATES 2026
[8 empty] | PRE-RAMADAN LAUNCH |  | RAMADAN LAUNCHES
MONTHS |  |  | DEC'25 |  |  |  | JAN'26 |  |  |  |  | FEB'26 |  |  |  | MAR'26 |  |  |  | APR'25 |  |  |  |  | MAY'26 |  |  |  | JUN'26
HIT |  |  | SS26 - HIT 1 |  |  |  | SS26 - HIT 2 |  |  |  |  | SS26 - HIT 3 |  |  |  | SS26 - HIT 4 |  |  |  | SS26 - HIT 5 |  |  |  |  | SS26 - HIT 6 |  |  |  | SS26 - HIT 7
GRN WK Considering 7D |  |  | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52
GRN WK Considering 10D for Ramadan (Follow this for Jan /Feb / Mar)
GRN DATE |  |  | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21
Launch Sequence |  |  | 2025-11-30: Launch 1; 2025-12-14: Launch 2; 2026-01-04: Launch 1; 2026-01-18: Launch 2; 2026-02-01: Launch 1; 2026-02-15: Launch 2; 2026-03-01: Launch 1; 2026-03-15: Launch 2; 2026-03-29: Launch 1; 2026-04-12: Launch 2; 2026-05-03: Launch 1; 2026-05-17: Launch 2; 2026-05-31: Launch 1; 2026-06-14: Launch 2
Drop |  |  | 2025-11-30: Transition line; 2025-12-14: Transition line; 2026-01-04: Pre-Ramadan; 2026-01-18: Ramadan Drop 1; 2026-02-01: Ramadan Drop 2; 2026-02-15: Ramadan Drop 3; 2026-03-01: Ramadan Drop 4
Monthly Drop Split |  |  | 2025-11-30: 60%; 2025-12-14: 40%; 2026-01-04: 50%; 2026-01-18: 50%; 2026-02-01: 70%; 2026-02-15: 30%; 2026-03-01: 70%; 2026-03-15: 30%; 2026-03-29: 60%; 2026-04-12: 40%; 2026-05-03: 60%; 2026-05-17: 40%; 2026-05-31: 60%; 2026-06-14: 40%
LAUNCH WK |  |  | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52 | WK0
LAUNCH DATE |  |  | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28
Milestone | Duration | Calculation Guideline
Trend Presentation | 21 | Range Build - 21 days
Merch Direction | 28 | Budget handover - 28 days | 2025-12-14: 12th May - 16th May
Vendor Week
|  |  | Hit 1 Laydown |  |  |  | Hit 2 Laydown |  |  |  |  | Hit 3 Laydown |  |  |  | Hit 4 Laydown |  |  |  | Hit 5 Laydown |  |  |  |  | Hit 6 Laydown |  |  |  | Hit 7 Laydown
Range build | 2 | Techpack handover - 42 days | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19
Tech Pack Handover | 8 | Pre-Laydown - 24 days | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21
Laydown | 2 | Supplier Commitment - 7 days | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29
Supplier Commitment Date via Buying Notes + Briefing | 75 | Laydown + 7 days | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-09-30 | 2025-10-07 | 2025-10-14 | 2025-10-21 | 2025-10-28 | 2025-11-04 | 2025-11-11 | 2025-11-16 | 2025-11-16 | 2025-11-16 | 2025-11-16 | 2025-11-16 | 2025-11-25 | 2025-12-02 | 2025-12-09 | 2025-12-16 | 2025-12-23 | 2025-12-30 | 2026-01-06 | 2026-01-13 | 2026-01-20 | 2026-01-27 | 2026-02-03 | 2026-03-10 | 2026-03-17 | 2026-03-24 | 2026-03-31
Distribution Handover by Planners | 2 | Laydown + 14 days | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-09-30 | 2025-10-07 | 2025-10-14 | 2025-10-21 | 2025-10-28 | 2025-11-04 | 2025-11-11 | 2025-11-16 | 2025-11-16 | 2025-11-16 | 2025-11-16 | 2025-11-16 | 2025-11-25 | 2025-12-02 | 2025-12-09 | 2025-12-16 | 2025-12-23 | 2025-12-30 | 2026-01-06 | 2026-01-13 | 2026-01-20 | 2026-01-27 | 2026-02-03 | 2026-03-10 | 2026-03-17 | 2026-03-24 | 2026-03-31
PO Upload in OTS + Approval from Finance) | 2 | Distribution planning + 7 days | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-18 | 2025-11-18 | 2025-11-18 | 2025-11-18 | 2025-11-18 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02
ADDITIONAL BUFFER | 0
Shipment start date (All Countries by Air) | 7 | Shipment end date - 7 days | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07
Shipment end date (All Countries by Air) | 7 | RDC GRN - shipment lead time | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14
RDC GRN DATE | 7 |  | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21
Launch Date | 0 |  | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28
Additional days for Ramadan | 3
| 101 | #VALUE! | 2025-12-07: 101; 2025-12-21: 101; 2026-01-04: 101; 2026-01-18: 101; 2026-02-08: 101; 2026-02-22: 110; 2026-03-08: 124; 2026-03-22: 129; 2026-04-05: 129; 2026-04-19: 129; 2026-05-10: 129; 2026-05-24: 129; 2026-06-07: 101; 2026-06-21: 101

## QR_60D
REGULAR CRITICAL PATH | [11 empty] | CNY + FACTORY CLOSURE DATES 2025
EVENTS |  |  |  | EOSS - TENTATIVE (17 DEC FOR 3WK) | [8 empty] | RAMADAN DATES 2026
[8 empty] | PRE-RAMADAN LAUNCH |  | RAMADAN LAUNCHES
MONTHS |  |  | DEC'25 |  |  |  | JAN'26 |  |  |  |  | FEB'26 |  |  |  | MAR'26 |  |  |  | APR'25 |  |  |  |  | MAY'26 |  |  |  | JUN'26
HIT |  |  | SS26 - HIT 1 |  |  |  | SS26 - HIT 2 |  |  |  |  | SS26 - HIT 3 |  |  |  | SS26 - HIT 4 |  |  |  | SS26 - HIT 5 |  |  |  |  | SS26 - HIT 6 |  |  |  | SS26 - HIT 7
GRN WK Considering 7D |  |  | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52
GRN WK Considering 10D for Ramadan (Follow this for Jan /Feb / Mar)
GRN DATE |  |  | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21
Launch Sequence |  |  | 2025-11-30: Launch 1; 2025-12-14: Launch 2; 2026-01-04: Launch 1; 2026-01-18: Launch 2; 2026-02-01: Launch 1; 2026-02-15: Launch 2; 2026-03-01: Launch 1; 2026-03-15: Launch 2; 2026-03-29: Launch 1; 2026-04-12: Launch 2; 2026-05-03: Launch 1; 2026-05-17: Launch 2; 2026-05-31: Launch 1; 2026-06-14: Launch 2
Drop |  |  | 2025-11-30: Transition line; 2025-12-14: Transition line; 2026-01-04: Pre-Ramadan; 2026-01-18: Ramadan Drop 1; 2026-02-01: Ramadan Drop 2; 2026-02-15: Ramadan Drop 3; 2026-03-01: Ramadan Drop 4
Monthly Drop Split |  |  | 2025-11-30: 60%; 2025-12-14: 40%; 2026-01-04: 50%; 2026-01-18: 50%; 2026-02-01: 70%; 2026-02-15: 30%; 2026-03-01: 70%; 2026-03-15: 30%; 2026-03-29: 60%; 2026-04-12: 40%; 2026-05-03: 60%; 2026-05-17: 40%; 2026-05-31: 60%; 2026-06-14: 40%
LAUNCH WK |  |  | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52 | WK0
LAUNCH DATE |  |  | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28
Milestone | Duration | Calculation Guideline
Trend Presentation | 21 | Range Build - 21 days
Merch Direction | 28 | Budget handover - 28 days | 2025-12-14: 12th May - 16th May
Vendor Week
|  |  | Hit 1 Laydown |  |  |  | Hit 2 Laydown |  |  |  |  | Hit 3 Laydown |  |  |  | Hit 4 Laydown |  |  |  | Hit 5 Laydown |  |  |  |  | Hit 6 Laydown |  |  |  | Hit 7 Laydown
Range build | 2 | Techpack handover - 42 days | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-10 | 2025-10-17 | 2025-10-24 | 2025-10-31 | 2025-11-07 | 2025-11-14 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-28 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2025-12-26 | 2026-01-02 | 2026-01-09 | 2026-01-16 | 2026-01-23 | 2026-02-27 | 2026-03-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03
Tech Pack Handover | 8 | Pre-Laydown - 24 days | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05
Laydown | 2 | Supplier Commitment - 7 days | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13
Supplier Commitment Date via Buying Notes + Briefing | 60 | Laydown + 7 days | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-29 | 2025-11-05 | 2025-11-12 | 2025-11-19 | 2025-11-26 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-10 | 2025-12-17 | 2025-12-24 | 2025-12-31 | 2026-01-07 | 2026-01-14 | 2026-01-21 | 2026-01-28 | 2026-02-04 | 2026-03-11 | 2026-03-18 | 2026-03-25 | 2026-04-01 | 2026-04-08 | 2026-04-15
Distribution Handover by Planners | 2 | Laydown + 14 days | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-29 | 2025-11-05 | 2025-11-12 | 2025-11-19 | 2025-11-26 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-10 | 2025-12-17 | 2025-12-24 | 2025-12-31 | 2026-01-07 | 2026-01-14 | 2026-01-21 | 2026-01-28 | 2026-02-04 | 2026-03-11 | 2026-03-18 | 2026-03-25 | 2026-04-01 | 2026-04-08 | 2026-04-15
PO Upload in OTS + Approval from Finance) | 2 | Distribution planning + 7 days | 2025-09-26 | 2025-10-03 | 2025-10-10 | 2025-10-17 | 2025-10-24 | 2025-10-31 | 2025-11-07 | 2025-11-14 | 2025-11-21 | 2025-11-28 | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-12 | 2025-12-19 | 2025-12-26 | 2026-01-02 | 2026-01-09 | 2026-01-16 | 2026-01-23 | 2026-01-30 | 2026-02-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10 | 2026-04-17
ADDITIONAL BUFFER | 0
Shipment start date (All Countries by Air) | 7 | Shipment end date - 7 days | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07
Shipment end date (All Countries by Air) | 7 | RDC GRN - shipment lead time | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14
RDC GRN DATE | 7 |  | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21
Launch Date | 0 |  | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28
Additional days for Ramadan | 3
| 86 | #VALUE! | 2025-12-07: 86; 2025-12-21: 86; 2026-01-04: 86; 2026-01-18: 86; 2026-02-08: 86; 2026-02-22: 95; 2026-03-08: 109; 2026-03-22: 114; 2026-04-05: 114; 2026-04-19: 114; 2026-05-10: 114; 2026-05-24: 86; 2026-06-07: 86; 2026-06-21: 86

## QR_45D
REGULAR CRITICAL PATH | [11 empty] | CNY + FACTORY CLOSURE DATES 2025
EVENTS |  |  |  | EOSS - TENTATIVE (17 DEC FOR 3WK) | [8 empty] | RAMADAN DATES 2026
[8 empty] | PRE-RAMADAN LAUNCH |  | RAMADAN LAUNCHES
MONTHS |  |  | DEC'25 |  |  |  | JAN'26 |  |  |  |  | FEB'26 |  |  |  | MAR'26 |  |  |  | APR'25 |  |  |  |  | MAY'26 |  |  |  | JUN'26
HIT |  |  | SS26 - HIT 1 |  |  |  | SS26 - HIT 2 |  |  |  |  | SS26 - HIT 3 |  |  |  | SS26 - HIT 4 |  |  |  | SS26 - HIT 5 |  |  |  |  | SS26 - HIT 6 |  |  |  | SS26 - HIT 7
GRN WK Considering 7D |  |  | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52
GRN WK Considering 10D for Ramadan (Follow this for Jan /Feb / Mar)
GRN DATE |  |  | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21
Launch Sequence |  |  | 2025-11-30: Launch 1; 2025-12-14: Launch 2; 2026-01-04: Launch 1; 2026-01-18: Launch 2; 2026-02-01: Launch 1; 2026-02-15: Launch 2; 2026-03-01: Launch 1; 2026-03-15: Launch 2; 2026-03-29: Launch 1; 2026-04-12: Launch 2; 2026-05-03: Launch 1; 2026-05-17: Launch 2; 2026-05-31: Launch 1; 2026-06-14: Launch 2
Drop |  |  | 2025-11-30: Transition line; 2025-12-14: Transition line; 2026-01-04: Pre-Ramadan; 2026-01-18: Ramadan Drop 1; 2026-02-01: Ramadan Drop 2; 2026-02-15: Ramadan Drop 3; 2026-03-01: Ramadan Drop 4
Monthly Drop Split |  |  | 2025-11-30: 60%; 2025-12-14: 40%; 2026-01-04: 50%; 2026-01-18: 50%; 2026-02-01: 70%; 2026-02-15: 30%; 2026-03-01: 70%; 2026-03-15: 30%; 2026-03-29: 60%; 2026-04-12: 40%; 2026-05-03: 60%; 2026-05-17: 40%; 2026-05-31: 60%; 2026-06-14: 40%
LAUNCH WK |  |  | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52 | WK0
LAUNCH DATE |  |  | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28
Milestone | Duration | Calculation Guideline
Trend Presentation | 21 | Range Build - 21 days
Merch Direction | 28 | Budget handover - 28 days | 2025-12-14: 12th May - 16th May
Vendor Week
|  |  | Hit 1 Laydown |  |  |  | Hit 2 Laydown |  |  |  |  | Hit 3 Laydown |  |  |  | Hit 4 Laydown |  |  |  | Hit 5 Laydown |  |  |  |  | Hit 6 Laydown |  |  |  | Hit 7 Laydown
Range build | 2 | Techpack handover - 42 days | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2025-12-04 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18
Tech Pack Handover | 8 | Pre-Laydown - 24 days | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20
Laydown | 2 | Supplier Commitment - 7 days | 2025-10-07 | 2025-10-14 | 2025-10-21 | 2025-10-28 | 2025-11-04 | 2025-11-11 | 2025-11-18 | 2025-11-25 | 2025-12-02 | 2025-12-09 | 2025-12-14 | 2025-12-14 | 2025-12-14 | 2025-12-14 | 2025-12-14 | 2025-12-23 | 2025-12-30 | 2026-01-06 | 2026-01-13 | 2026-01-20 | 2026-01-27 | 2026-02-03 | 2026-03-10 | 2026-03-17 | 2026-03-24 | 2026-03-31 | 2026-04-07 | 2026-04-14 | 2026-04-21 | 2026-04-28
Supplier Commitment Date via Buying Notes + Briefing | 45 | Laydown + 7 days | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-09 | 2026-04-16 | 2026-04-23 | 2026-04-30
Distribution Handover by Planners | 2 | Laydown + 14 days | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-09 | 2026-04-16 | 2026-04-23 | 2026-04-30
PO Upload in OTS + Approval from Finance) | 2 | Distribution planning + 7 days | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01 | 2025-11-08 | 2025-11-15 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-27 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25 | 2026-05-02
ADDITIONAL BUFFER | 0
Shipment start date (All Countries by Air) | 7 | Shipment end date - 7 days | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07
Shipment end date (All Countries by Air) | 7 | RDC GRN - shipment lead time | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14
RDC GRN DATE | 7 |  | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21
Launch Date | 0 |  | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28
Additional days for Ramadan | 3
| 71 | #VALUE! | 2025-12-07: 71; 2025-12-21: 71; 2026-01-04: 71; 2026-01-18: 71; 2026-02-08: 71; 2026-02-22: 80; 2026-03-08: 94; 2026-03-22: 99; 2026-04-05: 99; 2026-04-19: 99; 2026-05-10: 71; 2026-05-24: 71; 2026-06-07: 71; 2026-06-21: 71

## QR_30D
REGULAR CRITICAL PATH | [11 empty] | CNY + FACTORY CLOSURE DATES 2025
EVENTS |  |  |  | EOSS - TENTATIVE (17 DEC FOR 3WK) | [8 empty] | RAMADAN DATES 2026
[8 empty] | PRE-RAMADAN LAUNCH |  | RAMADAN LAUNCHES
MONTHS |  |  | DEC'25 |  |  |  | JAN'26 |  |  |  |  | FEB'26 |  |  |  | MAR'26 |  |  |  | APR'25 |  |  |  |  | MAY'26 |  |  |  | JUN'26
HIT |  |  | SS26 - HIT 1 |  |  |  | SS26 - HIT 2 |  |  |  |  | SS26 - HIT 3 |  |  |  | SS26 - HIT 4 |  |  |  | SS26 - HIT 5 |  |  |  |  | SS26 - HIT 6 |  |  |  | SS26 - HIT 7
GRN WK Considering 7D |  |  | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52
GRN WK Considering 10D for Ramadan (Follow this for Jan /Feb / Mar)
GRN DATE |  |  | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21
Launch Sequence |  |  | 2025-11-30: Launch 1; 2025-12-14: Launch 2; 2026-01-04: Launch 1; 2026-01-18: Launch 2; 2026-02-01: Launch 1; 2026-02-15: Launch 2; 2026-03-01: Launch 1; 2026-03-15: Launch 2; 2026-03-29: Launch 1; 2026-04-12: Launch 2; 2026-05-03: Launch 1; 2026-05-17: Launch 2; 2026-05-31: Launch 1; 2026-06-14: Launch 2
Drop |  |  | 2025-11-30: Transition line; 2025-12-14: Transition line; 2026-01-04: Pre-Ramadan; 2026-01-18: Ramadan Drop 1; 2026-02-01: Ramadan Drop 2; 2026-02-15: Ramadan Drop 3; 2026-03-01: Ramadan Drop 4
Monthly Drop Split |  |  | 2025-11-30: 60%; 2025-12-14: 40%; 2026-01-04: 50%; 2026-01-18: 50%; 2026-02-01: 70%; 2026-02-15: 30%; 2026-03-01: 70%; 2026-03-15: 30%; 2026-03-29: 60%; 2026-04-12: 40%; 2026-05-03: 60%; 2026-05-17: 40%; 2026-05-31: 60%; 2026-06-14: 40%
LAUNCH WK |  |  | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52 | WK0
LAUNCH DATE |  |  | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28
Milestone | Duration | Calculation Guideline
Trend Presentation | 21 | Range Build - 21 days
Merch Direction | 28 | Budget handover - 28 days | 2025-12-14: 12th May - 16th May
Vendor Week
|  |  | Hit 1 Laydown |  |  |  | Hit 2 Laydown |  |  |  |  | Hit 3 Laydown |  |  |  | Hit 4 Laydown |  |  |  | Hit 5 Laydown |  |  |  |  | Hit 6 Laydown |  |  |  | Hit 7 Laydown
Range build | 2 | Techpack handover - 42 days | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03
Tech Pack Handover | 8 | Pre-Laydown - 24 days | 2025-10-14 | 2025-10-21 | 2025-10-28 | 2025-11-04 | 2025-11-11 | 2025-11-18 | 2025-11-25 | 2025-12-02 | 2025-12-09 | 2025-12-16 | 2025-12-21 | 2025-12-21 | 2025-12-21 | 2025-12-21 | 2025-12-21 | 2025-12-30 | 2026-01-06 | 2026-01-13 | 2026-01-20 | 2026-01-27 | 2026-03-03 | 2026-03-10 | 2026-03-17 | 2026-03-24 | 2026-03-31 | 2026-04-07 | 2026-04-14 | 2026-04-21 | 2026-04-28 | 2026-05-05
Laydown | 2 | Supplier Commitment - 7 days | 2025-10-22 | 2025-10-29 | 2025-11-05 | 2025-11-12 | 2025-11-19 | 2025-11-26 | 2025-12-03 | 2025-12-10 | 2025-12-17 | 2025-12-24 | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2026-01-07 | 2026-01-14 | 2026-01-21 | 2026-01-28 | 2026-02-04 | 2026-03-11 | 2026-03-18 | 2026-03-25 | 2026-04-01 | 2026-04-08 | 2026-04-15 | 2026-04-22 | 2026-04-29 | 2026-05-06 | 2026-05-13
Supplier Commitment Date via Buying Notes + Briefing | 30 | Laydown + 7 days | 2025-10-24 | 2025-10-31 | 2025-11-07 | 2025-11-14 | 2025-11-21 | 2025-11-28 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2025-12-26 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2026-01-09 | 2026-01-16 | 2026-01-23 | 2026-01-30 | 2026-02-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10 | 2026-04-17 | 2026-04-24 | 2026-05-01 | 2026-05-08 | 2026-05-15
Distribution Handover by Planners | 2 | Laydown + 14 days | 2025-10-24 | 2025-10-31 | 2025-11-07 | 2025-11-14 | 2025-11-21 | 2025-11-28 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2025-12-26 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2026-01-09 | 2026-01-16 | 2026-01-23 | 2026-01-30 | 2026-02-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10 | 2026-04-17 | 2026-04-24 | 2026-05-01 | 2026-05-08 | 2026-05-15
PO Upload in OTS + Approval from Finance) | 2 | Distribution planning + 7 days | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-02 | 2026-01-02 | 2026-01-02 | 2026-01-02 | 2026-01-02 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17
ADDITIONAL BUFFER | 0
Shipment start date (All Countries by Air) | 7 | Shipment end date - 7 days | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07
Shipment end date (All Countries by Air) | 7 | RDC GRN - shipment lead time | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14
RDC GRN DATE | 7 |  | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21
Launch Date | 0 |  | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28
Additional days for Ramadan | 3
| 56 | #REF! | 2025-12-07: 56; 2025-12-21: 56; 2026-01-04: 56; 2026-01-18: 56; 2026-02-08: 56; 2026-02-22: 65; 2026-03-08: 79; 2026-03-22: 84; 2026-04-05: 84; 2026-04-19: 84; 2026-05-10: 56; 2026-05-24: 56; 2026-06-07: 56; 2026-06-21: 56