## Calendar Events + Assumptions
Only Edit these Dates |  |  | Autocalculated: Not to be edited
| Chinese New Year Date(2025) | 2025-01-29 |  | Factory Closure Dates (CN) | Start | 2025-01-19 | Production Buffer (in days) | 28
[5 empty] | End | 2025-02-16
| Ramadan Dates (2025) | 2025-02-27 |  | Shipment Cutoff Date (CN) | 2025-01-11 | (18 days prior to CNY as CFS would take ~10-15 days for processing)
|  | 2025-03-29 |  | Shipment Resumption Date (CN) | 2025-02-16 | (18 days later)
|  |  |  | Extra GRN Days for Ramadan | 3
| Pongal Dates (2025) | 2025-01-14 |  | Factory Closure Dates (IN) | Start | 2025-01-09 | Production Buffer (in days) | 10
|  | 2025-01-17 |  |  | End | 2025-01-19
| Eid Holidays (BD) (2025) | 2025-03-27 |  | Shipment Cut Off (BD) | Start | 2025-03-22 | Production Buffer (in days) | 19
|  | 2025-04-05 |  | Shipment resumption (BD) | End | 2025-04-10
| Diwali 2025 | 2025-10-20 |  | Shipment Cut Off (IN) | Start | 2025-10-15 | Production Buffer (in days) | 16
|  | 2025-10-21 |  | Shipment resumption (IN) | End | 2025-10-31
Notes -
1. Hit 1 Launch 1 moved to 10th July and GRN 3rd July considering stock at end of year
2. Buying notes is ooficial PO date - start production lead time
3. Production buffer + Shipment cut-off dates built in India for Diwali

## REGULAR CP_90D
REGULAR CRITICAL PATH
EVENTS
WHITE WEDNESDAY SALE
MONTHS |  |  | JUL'25 |  |  |  |  | AUG'25 |  |  |  | SEP'25 |  |  |  | OCT'25 |  |  |  |  | NOV'25 |  |  |  | DEC'25
HIT |  |  | WN25 - HIT 1 |  |  |  |  | WN25 - HIT 2 |  |  |  | WN25 - HIT 3 |  |  |  | WN25 - HIT 4 |  |  |  |  | WN25 - HIT 5 |  |  |  | SS26 HIT 1
GRN WK Considering 7D |  |  | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26
GRN WK Considering 10D for Ramadan (Follow this for Jan /Feb / Mar)
GRN DATE |  |  | 2025-07-03 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21
Launch Sequence |  |  | 2025-07-03: Launch 1; 2025-07-13: Launch 2; 2025-08-03: Launch 1; 2025-08-17: Launch 2; 2025-08-31: Launch 1; 2025-09-14: Launch 2; 2025-09-28: Launch 1; 2025-10-12: Launch 2; 2025-11-02: Launch 1; 2025-11-16: Launch 2; 2025-11-30: Launch 1; 2025-12-14: Launch 2
LAUNCH WK |  |  | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27
LAUNCH DATE |  |  | 2025-07-10 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28
Milestone | Duration | Calculation Guideline
Trend Presentation | 21 | Range Build - 21 days | 2025-07-10: 1st Nov - 7th Nov
Merch Direction | 28 | Budget handover - 28 days | 2025-07-10: 9th Dec - 17th Dec
Vendor Week
|  |  | Hit 1 Laydown |  |  |  |  | Hit 2 Laydown |  |  |  | Hit 3 Laydown |  |  |  | Hit 4 Laydown |  |  |  |  | Hit 5 Laydown |  |  |  | Hit 6 Laydown
Range build | 30 | Techpack handover - 42 days | 2024-11-09 | 2024-12-10 | 2024-12-17 | 2024-12-24 | 2024-12-31 | 2025-01-07 | 2025-01-14 | 2025-01-21 | 2025-01-28 | 2025-02-04 | 2025-02-11 | 2025-02-18 | 2025-02-25 | 2025-03-04 | 2025-03-11 | 2025-03-18 | 2025-03-25 | 2025-04-01 | 2025-04-08 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27
Tech Pack Handover | 24 | Pre-Laydown - 24 days | 2024-12-09 | 2025-01-09 | 2025-01-16 | 2025-01-23 | 2025-01-30 | 2025-02-06 | 2025-02-13 | 2025-02-20 | 2025-02-27 | 2025-03-06 | 2025-03-13 | 2025-03-20 | 2025-03-27 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26
Planning budget handover | 7 | Pre-Laydown - 7 days | 2024-12-26 | 2025-01-26 | 2025-02-02 | 2025-02-09 | 2025-02-16 | 2025-02-23 | 2025-03-02 | 2025-03-09 | 2025-03-16 | 2025-03-23 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-20 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-08 | 2025-06-15 | 2025-06-22 | 2025-06-29 | 2025-07-06 | 2025-07-13
Pre Laydown | 7 | Laydown - 7 days | 2025-01-02 | 2025-02-02 | 2025-02-09 | 2025-02-16 | 2025-02-23 | 2025-03-02 | 2025-03-09 | 2025-03-16 | 2025-03-23 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-20 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-08 | 2025-06-15 | 2025-06-22 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20
Laydown | 7 | Supplier Commitment - 7 days | 2025-01-09 | 2025-02-09 | 2025-02-16 | 2025-02-23 | 2025-03-02 | 2025-03-09 | 2025-03-16 | 2025-03-23 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-20 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-08 | 2025-06-15 | 2025-06-22 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27
Supplier Commitment Date via Buying Notes + Briefing | 90 | Laydown + 7 days | 2025-01-16 | 2025-02-16 | 2025-02-23 | 2025-03-02 | 2025-03-09 | 2025-03-16 | 2025-03-23 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-20 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-08 | 2025-06-15 | 2025-06-22 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03
Distribution Handover by Planners | 14 | Laydown + 14 days | 2025-01-23 | 2025-02-23 | 2025-03-02 | 2025-03-09 | 2025-03-16 | 2025-03-23 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-20 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-08 | 2025-06-15 | 2025-06-22 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10
PO Upload in OTS + Approval from Finance) | 7 | Distribution planning + 7 days | 2025-01-30 | 2025-03-02 | 2025-03-09 | 2025-03-16 | 2025-03-23 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-20 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-08 | 2025-06-15 | 2025-06-22 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17
Development Sample Approval | 60 | LSD - 60D | 2025-03-15 | 2025-03-18 | 2025-03-25 | 2025-04-01 | 2025-04-08 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02
PP/GPT Approval | 30 | LSD - 30D | 2025-04-14 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02
TOP Approval | 10 | LSD - 10D | 2025-05-04 | 2025-05-07 | 2025-05-14 | 2025-05-21 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22
ADDITIONAL BUFFER | 5
Shipment start date (Central china/ Turkey/ Cambodia) | 7 | Shipment end date - 7 days | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment end date (Central china/ Turkey/ Cambodia) | 45 | RDC GRN - shipment lead time | 2025-05-14 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01
Shipment start date (North China) | 7 | Shipment end date - 7 days | 2025-04-30 | 2025-05-03 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18
Shipment end date (North China) | 52 | RDC GRN - shipment lead time | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment start date (Bangladesh) | 7 | Shipment end date - 7 days | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment end date (Bangladesh) | 45 | RDC GRN - shipment lead time | 2025-05-14 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01
Shipment start date (India,Pakistan, SL) | 7 | Shipment end date - 7 days | 2025-05-19 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-30 | 2025-11-06
Shipment end date (India, Pakistan, SL) | 33 | RDC GRN - shipment lead time | 2025-05-26 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-11-06 | 2025-11-13
Shipment start date ( Indonesia, Vietnam, Thailand) | 7 | Shipment end date - 7 days | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment end date ( Indonesia, Vietnam, Thailand) | 45 | RDC GRN - shipment lead time | 2025-05-14 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01
RDC GRN DATE | 7 |  | 2025-07-03 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21
Launch Date | 0 |  | 2025-07-10 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28
Additional days for Ramadan | 3
| 215 | #REF! | 2025-07-10: 243; 2025-07-20: 215; 2025-08-10: 215; 2025-08-24: 215; 2025-09-07: 215; 2025-09-21: 215; 2025-10-05: 215; 2025-10-19: 215; 2025-11-09: 215; 2025-11-23: 215; 2025-12-07: 215; 2025-12-21: 215

## REGULAR CP_120D
REGULAR CRITICAL PATH
EVENTS
WHITE WEDNESDAY SALE
MONTHS |  |  | JUL'25 |  |  |  |  | AUG'25 |  |  |  | SEP'25 |  |  |  | OCT'25 |  |  |  |  | NOV'25 |  |  |  | DEC'25
HIT |  |  | WN25 - HIT 1 |  |  |  |  | WN25 - HIT 2 |  |  |  | WN25 - HIT 3 |  |  |  | WN25 - HIT 4 |  |  |  |  | WN25 - HIT 5 |  |  |  | SS26 HIT 1
GRN WK Considering 7D |  |  | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26
GRN WK Considering 10D for Ramadan (Follow this for Jan /Feb / Mar)
GRN DATE |  |  | 2025-07-03 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21
Launch Sequence |  |  | 2025-07-03: Launch 1; 2025-07-13: Launch 2; 2025-08-03: Launch 1; 2025-08-17: Launch 2; 2025-08-31: Launch 1; 2025-09-14: Launch 2; 2025-09-28: Launch 1; 2025-10-12: Launch 2; 2025-11-02: Launch 1; 2025-11-16: Launch 2; 2025-11-30: Launch 1; 2025-12-14: Launch 2
LAUNCH WK |  |  | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27
LAUNCH DATE |  |  | 2025-07-10 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28
Milestone | Duration | Calculation Guideline
Trend Presentation | 21 | Range Build - 21 days | 2025-07-10: 1st Nov - 7th Nov
Merch Direction (initial OTB) | 28 | Budget handover - 28 days | 2025-07-10: 9th Dec - 17th Dec
Vendor Week
|  |  | Hit 1 Laydown |  |  |  |  | Hit 2 Laydown |  |  |  | Hit 3 Laydown |  |  |  | Hit 4 Laydown |  |  |  |  | Hit 5 Laydown |  |  |  | Hit 6 Laydown
Range build | 30 | Techpack handover - 42 days | 2024-10-10 | 2024-10-13 | 2024-10-20 | 2024-10-27 | 2024-11-03 | 2024-11-10 | 2024-12-15 | 2024-12-22 | 2024-12-29 | 2025-01-05 | 2025-01-12 | 2025-01-19 | 2025-01-26 | 2025-02-02 | 2025-02-09 | 2025-02-16 | 2025-02-23 | 2025-03-02 | 2025-03-09 | 2025-03-16 | 2025-03-23 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-20 | 2025-04-27
Tech Pack Handover (Design team- image+season+discription) | 24 | Pre-Laydown - 24 days | 2024-11-09 | 2024-11-12 | 2024-11-19 | 2024-11-26 | 2024-12-03 | 2024-12-10 | 2025-01-14 | 2025-01-21 | 2025-01-28 | 2025-02-04 | 2025-02-11 | 2025-02-18 | 2025-02-25 | 2025-03-04 | 2025-03-11 | 2025-03-18 | 2025-03-25 | 2025-04-01 | 2025-04-08 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27
Planning budget handover | 7 | Pre-Laydown - 7 days | 2024-11-26 | 2024-11-29 | 2024-12-06 | 2024-12-13 | 2024-12-20 | 2024-12-27 | 2025-01-31 | 2025-02-07 | 2025-02-14 | 2025-02-21 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-04-04 | 2025-04-11 | 2025-04-18 | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13
Pre Laydown | 7 | Laydown - 7 days | 2024-12-03 | 2024-12-06 | 2024-12-13 | 2024-12-20 | 2024-12-27 | 2025-01-03 | 2025-02-07 | 2025-02-14 | 2025-02-21 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-04-04 | 2025-04-11 | 2025-04-18 | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20
Laydown | 7 | Supplier Commitment - 7 days | 2024-12-10 | 2024-12-13 | 2024-12-20 | 2024-12-27 | 2025-01-03 | 2025-01-10 | 2025-02-14 | 2025-02-21 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-04-04 | 2025-04-11 | 2025-04-18 | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27
Supplier Commitment Date via Buying Notes + Briefing | 120 | Laydown + 7 days | 2024-12-17 | 2024-12-20 | 2024-12-27 | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-02-21 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-04-04 | 2025-04-11 | 2025-04-18 | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04
Distribution Handover by Planners- Launch plan dates- quantity and territory | 14 | Laydown + 14 days | 2024-12-24 | 2024-12-27 | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-01-24 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-04-04 | 2025-04-11 | 2025-04-18 | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11
PO Upload in OTS + Approval from Finance)- Buyer | 7 | Distribution planning + 7 days | 2024-12-31 | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-01-24 | 2025-01-31 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-04-04 | 2025-04-11 | 2025-04-18 | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18
Development Sample Approval | 60 | LSD - 60D | 2025-03-15 | 2025-03-18 | 2025-03-25 | 2025-04-01 | 2025-04-08 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02
PP/GPT Approval | 30 | LSD - 30D | 2025-04-14 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02
TOP Approval | 10 | LSD - 10D | 2025-05-04 | 2025-05-07 | 2025-05-14 | 2025-05-21 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22
ADDITIONAL BUFFER | 5
Shipment start date (Central china/ Turkey/ Cambodia) | 7 | Shipment end date - 7 days | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment end date (Central china/ Turkey/ Cambodia) | 45 | RDC GRN - shipment lead time | 2025-05-14 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01
Shipment start date (North China) | 7 | Shipment end date - 7 days | 2025-04-30 | 2025-05-03 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18
Shipment end date (North China) | 52 | RDC GRN - shipment lead time | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment start date (Bangladesh) | 7 | Shipment end date - 7 days | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment end date (Bangladesh) | 45 | RDC GRN - shipment lead time | 2025-05-14 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01
Shipment start date (India,Pakistan, SL) | 7 | Shipment end date - 7 days | 2025-05-19 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-30 | 2025-11-06
Shipment end date (India, Pakistan, SL) | 33 | RDC GRN - shipment lead time | 2025-05-26 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-11-06 | 2025-11-13
Shipment start date ( Indonesia, Vietnam, Thailand) | 7 | Shipment end date - 7 days | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment end date ( Indonesia, Vietnam, Thailand) | 45 | RDC GRN - shipment lead time | 2025-05-14 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01
RDC GRN DATE | 7 |  | 2025-07-03 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21
Launch Date | 0 |  | 2025-07-10 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28
Additional days for Ramadan | 3
| 245 | #REF! | 2025-07-10: 273; 2025-07-20: 273; 2025-08-10: 273; 2025-08-24: 245; 2025-09-07: 245; 2025-09-21: 245; 2025-10-05: 245; 2025-10-19: 245; 2025-11-09: 245; 2025-11-23: 245; 2025-12-07: 245; 2025-12-21: 245
|  |  | 28D production buffer due to CNY impact |  | 28D production buffer due to CNY impact |  |  | 28D production buffer due to CNY impact

## REGULAR CP_105D
REGULAR CRITICAL PATH
EVENTS
WHITE WEDNESDAY SALE
MONTHS |  |  | JUL'25 |  |  |  |  | AUG'25 |  |  |  | SEP'25 |  |  |  | OCT'25 |  |  |  |  | NOV'25 |  |  |  | DEC'25
HIT |  |  | WN25 - HIT 1 |  |  |  |  | WN25 - HIT 2 |  |  |  | WN25 - HIT 3 |  |  |  | WN25 - HIT 4 |  |  |  |  | WN25 - HIT 5 |  |  |  | SS26 HIT 1
GRN WK Considering 7D |  |  | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26
GRN WK Considering 10D for Ramadan (Follow this for Jan /Feb / Mar)
GRN DATE |  |  | 2025-07-03 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21
Launch Sequence |  |  | 2025-07-03: Launch 1; 2025-07-13: Launch 2; 2025-08-03: Launch 1; 2025-08-17: Launch 2; 2025-08-31: Launch 1; 2025-09-14: Launch 2; 2025-09-28: Launch 1; 2025-10-12: Launch 2; 2025-11-02: Launch 1; 2025-11-16: Launch 2; 2025-11-30: Launch 1; 2025-12-14: Launch 2
LAUNCH WK |  |  | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27
LAUNCH DATE |  |  | 2025-07-10 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28
Milestone | Duration | Calculation Guideline
Trend Presentation | 21 | Range Build - 21 days | 2025-07-10: 1st Nov - 7th Nov
Merch Direction | 28 | Budget handover - 28 days | 2025-07-10: 9th Dec - 17th Dec
Vendor Week
|  |  | Hit 1 Laydown |  |  |  |  | Hit 2 Laydown |  |  |  | Hit 3 Laydown |  |  |  | Hit 4 Laydown |  |  |  |  | Hit 5 Laydown |  |  |  | Hit 6 Laydown
Range build | 30 | Techpack handover - 42 days | 2024-10-25 | 2024-10-28 | 2024-11-04 | 2024-11-11 | 2024-12-16 | 2024-12-23 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-20 | 2025-01-27 | 2025-02-03 | 2025-02-10 | 2025-02-17 | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-28 | 2025-05-05 | 2025-05-12
Tech Pack Handover | 24 | Pre-Laydown - 24 days | 2024-11-24 | 2024-11-27 | 2024-12-04 | 2024-12-11 | 2025-01-15 | 2025-01-22 | 2025-01-29 | 2025-02-05 | 2025-02-12 | 2025-02-19 | 2025-02-26 | 2025-03-05 | 2025-03-12 | 2025-03-19 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-16 | 2025-04-23 | 2025-04-30 | 2025-05-07 | 2025-05-14 | 2025-05-21 | 2025-05-28 | 2025-06-04 | 2025-06-11
Planning budget handover | 7 | Pre-Laydown - 7 days | 2024-12-11 | 2024-12-14 | 2024-12-21 | 2024-12-28 | 2025-02-01 | 2025-02-08 | 2025-02-15 | 2025-02-22 | 2025-03-01 | 2025-03-08 | 2025-03-15 | 2025-03-22 | 2025-03-29 | 2025-04-05 | 2025-04-12 | 2025-04-19 | 2025-04-26 | 2025-05-03 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28
Pre Laydown | 7 | Laydown - 7 days | 2024-12-18 | 2024-12-21 | 2024-12-28 | 2025-01-04 | 2025-02-08 | 2025-02-15 | 2025-02-22 | 2025-03-01 | 2025-03-08 | 2025-03-15 | 2025-03-22 | 2025-03-29 | 2025-04-05 | 2025-04-12 | 2025-04-19 | 2025-04-26 | 2025-05-03 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05
Laydown | 7 | Supplier Commitment - 7 days | 2024-12-25 | 2024-12-28 | 2025-01-04 | 2025-01-11 | 2025-02-15 | 2025-02-22 | 2025-03-01 | 2025-03-08 | 2025-03-15 | 2025-03-22 | 2025-03-29 | 2025-04-05 | 2025-04-12 | 2025-04-19 | 2025-04-26 | 2025-05-03 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12
Supplier Commitment Date via Buying Notes + Briefing | 105 | Laydown + 7 days | 2025-01-01 | 2025-01-04 | 2025-01-11 | 2025-01-18 | 2025-02-22 | 2025-03-01 | 2025-03-08 | 2025-03-15 | 2025-03-22 | 2025-03-29 | 2025-04-05 | 2025-04-12 | 2025-04-19 | 2025-04-26 | 2025-05-03 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19
Distribution Handover by Planners | 14 | Laydown + 14 days | 2025-01-08 | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-03-01 | 2025-03-08 | 2025-03-15 | 2025-03-22 | 2025-03-29 | 2025-04-05 | 2025-04-12 | 2025-04-19 | 2025-04-26 | 2025-05-03 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26
PO Upload in OTS + Approval from Finance) | 7 | Distribution planning + 7 days | 2025-01-15 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-03-08 | 2025-03-15 | 2025-03-22 | 2025-03-29 | 2025-04-05 | 2025-04-12 | 2025-04-19 | 2025-04-26 | 2025-05-03 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02
Development Sample Approval | 60 | LSD - 60D | 2025-03-15 | 2025-03-18 | 2025-03-25 | 2025-04-01 | 2025-04-08 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02
PP/GPT Approval | 30 | LSD - 30D | 2025-04-14 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02
TOP Approval | 10 | LSD - 10D | 2025-05-04 | 2025-05-07 | 2025-05-14 | 2025-05-21 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22
ADDITIONAL BUFFER | 5
Shipment start date (Central china/ Turkey/ Cambodia) | 7 | Shipment end date - 7 days | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment end date (Central china/ Turkey/ Cambodia) | 45 | RDC GRN - shipment lead time | 2025-05-14 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01
Shipment start date (North China) | 7 | Shipment end date - 7 days | 2025-04-30 | 2025-05-03 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18
Shipment end date (North China) | 52 | RDC GRN - shipment lead time | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment start date (Bangladesh) | 7 | Shipment end date - 7 days | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment end date (Bangladesh) | 45 | RDC GRN - shipment lead time | 2025-05-14 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01
Shipment start date (India,Pakistan, SL) | 7 | Shipment end date - 7 days | 2025-05-19 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-30 | 2025-11-06
Shipment end date (India, Pakistan, SL) | 33 | RDC GRN - shipment lead time | 2025-05-26 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-11-06 | 2025-11-13
Shipment start date ( Indonesia, Vietnam, Thailand) | 7 | Shipment end date - 7 days | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment end date ( Indonesia, Vietnam, Thailand) | 45 | RDC GRN - shipment lead time | 2025-05-14 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01
RDC GRN DATE | 7 |  | 2025-07-03 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21
Launch Date | 0 |  | 2025-07-10 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28
Additional days for Ramadan | 3
| 230 | #REF! | 2025-07-10: 258; 2025-07-20: 258; 2025-08-10: 230; 2025-08-24: 230; 2025-09-07: 230; 2025-09-21: 230; 2025-10-05: 230; 2025-10-19: 230; 2025-11-09: 230; 2025-11-23: 230; 2025-12-07: 230; 2025-12-21: 230
|  |  | 28D production buffer due to CNY impact |  | 28D production buffer due to CNY impact

## REGULAR CP_75D
REGULAR CRITICAL PATH
EVENTS
WHITE WEDNESDAY SALE
MONTHS |  |  | JUL'25 |  |  |  |  | AUG'25 |  |  |  | SEP'25 |  |  |  | OCT'25 |  |  |  |  | NOV'25 |  |  |  | DEC'25
HIT |  |  | WN25 - HIT 1 |  |  |  |  | WN25 - HIT 2 |  |  |  | WN25 - HIT 3 |  |  |  | WN25 - HIT 4 |  |  |  |  | WN25 - HIT 5 |  |  |  | SS26 HIT 1
GRN WK Considering 7D |  |  | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26
GRN WK Considering 10D for Ramadan (Follow this for Jan /Feb / Mar)
GRN DATE |  |  | 2025-07-03 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21
Launch Sequence |  |  | 2025-07-03: Launch 1; 2025-07-13: Launch 2; 2025-08-03: Launch 1; 2025-08-17: Launch 2; 2025-08-31: Launch 1; 2025-09-14: Launch 2; 2025-09-28: Launch 1; 2025-10-12: Launch 2; 2025-11-02: Launch 1; 2025-11-16: Launch 2; 2025-11-30: Launch 1; 2025-12-14: Launch 2
LAUNCH WK |  |  | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27
LAUNCH DATE |  |  | 2025-07-10 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28
Milestone | Duration | Calculation Guideline
Trend Presentation | 21 | Range Build - 21 days | 2025-07-10: 1st Nov - 7th Nov
Merch Direction | 28 | Budget handover - 28 days | 2025-07-10: 9th Dec - 17th Dec
Vendor Week
|  |  | Hit 1 Laydown |  |  |  |  | Hit 2 Laydown |  |  |  | Hit 3 Laydown |  |  |  | Hit 4 Laydown |  |  |  |  | Hit 5 Laydown |  |  |  | Hit 6 Laydown
Range build | 30 | Techpack handover - 42 days | 2024-12-22 | 2024-12-25 | 2025-01-01 | 2025-01-08 | 2025-01-15 | 2025-01-22 | 2025-01-29 | 2025-02-05 | 2025-02-12 | 2025-02-19 | 2025-02-26 | 2025-03-05 | 2025-03-12 | 2025-03-19 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-16 | 2025-04-23 | 2025-04-30 | 2025-05-07 | 2025-05-14 | 2025-05-21 | 2025-05-28 | 2025-06-04 | 2025-06-11
Tech Pack Handover | 24 | Pre-Laydown - 24 days | 2025-01-21 | 2025-01-24 | 2025-01-31 | 2025-02-07 | 2025-02-14 | 2025-02-21 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-04-04 | 2025-04-11 | 2025-04-18 | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11
Planning budget handover | 7 | Pre-Laydown - 7 days | 2025-02-07 | 2025-02-10 | 2025-02-17 | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-28 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-14 | 2025-07-21 | 2025-07-28
Pre Laydown | 7 | Laydown - 7 days | 2025-02-14 | 2025-02-17 | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-28 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04
Laydown | 7 | Supplier Commitment - 7 days | 2025-02-21 | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-28 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04 | 2025-08-11
Supplier Commitment Date via Buying Notes + Briefing | 75 | Laydown + 7 days | 2025-02-28 | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-28 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-18
Distribution Handover by Planners | 14 | Laydown + 14 days | 2025-03-07 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-28 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25
PO Upload in OTS + Approval from Finance) | 7 | Distribution planning + 7 days | 2025-03-14 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-28 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01
Development Sample Approval | 60 | LSD - 60D | 2025-03-15 | 2025-03-18 | 2025-03-25 | 2025-04-01 | 2025-04-08 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02
PP/GPT Approval | 30 | LSD - 30D | 2025-04-14 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02
TOP Approval | 10 | LSD - 10D | 2025-05-04 | 2025-05-07 | 2025-05-14 | 2025-05-21 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22
ADDITIONAL BUFFER | 5
Shipment start date (Central china/ Turkey/ Cambodia) | 7 | Shipment end date - 7 days | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment end date (Central china/ Turkey/ Cambodia) | 45 | RDC GRN - shipment lead time | 2025-05-14 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01
Shipment start date (North China) | 7 | Shipment end date - 7 days | 2025-04-30 | 2025-05-03 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18
Shipment end date (North China) | 52 | RDC GRN - shipment lead time | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment start date (Bangladesh) | 7 | Shipment end date - 7 days | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment end date (Bangladesh) | 45 | RDC GRN - shipment lead time | 2025-05-14 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01
Shipment start date (India,Pakistan, SL) | 7 | Shipment end date - 7 days | 2025-05-19 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-30 | 2025-11-06
Shipment end date (India, Pakistan, SL) | 33 | RDC GRN - shipment lead time | 2025-05-26 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-11-06 | 2025-11-13
Shipment start date ( Indonesia, Vietnam, Thailand) | 7 | Shipment end date - 7 days | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment end date ( Indonesia, Vietnam, Thailand) | 45 | RDC GRN - shipment lead time | 2025-05-14 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01
RDC GRN DATE | 7 |  | 2025-07-03 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21
Launch Date | 0 |  | 2025-07-10 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28
Additional days for Ramadan | 3
| 200 | #REF! | 2025-07-10: 200; 2025-07-20: 200; 2025-08-10: 200; 2025-08-24: 200; 2025-09-07: 200; 2025-09-21: 200; 2025-10-05: 200; 2025-10-19: 200; 2025-11-09: 200; 2025-11-23: 200; 2025-12-07: 200; 2025-12-21: 200
28D production buffer due to CNY impact

## REGULAR CP_60D
REGULAR CRITICAL PATH
EVENTS
WHITE WEDNESDAY SALE
MONTHS |  |  | JUL'25 |  |  |  |  | AUG'25 |  |  |  | SEP'25 |  |  |  | OCT'25 |  |  |  |  | NOV'25 |  |  |  | DEC'25
HIT |  |  | WN25 - HIT 1 |  |  |  |  | WN25 - HIT 2 |  |  |  | WN25 - HIT 3 |  |  |  | WN25 - HIT 4 |  |  |  |  | WN25 - HIT 5 |  |  |  | SS26 HIT 1
GRN WK Considering 7D |  |  | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26
GRN WK Considering 10D for Ramadan (Follow this for Jan /Feb / Mar)
GRN DATE |  |  | 2025-07-03 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21
Launch Sequence |  |  | 2025-07-03: Launch 1; 2025-07-13: Launch 2; 2025-08-03: Launch 1; 2025-08-17: Launch 2; 2025-08-31: Launch 1; 2025-09-14: Launch 2; 2025-09-28: Launch 1; 2025-10-12: Launch 2; 2025-11-02: Launch 1; 2025-11-16: Launch 2; 2025-11-30: Launch 1; 2025-12-14: Launch 2
LAUNCH WK |  |  | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27
LAUNCH DATE |  |  | 2025-07-10 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28
Milestone | Duration | Calculation Guideline
Trend Presentation | 21 | Range Build - 21 days | 2025-07-10: 1st Nov - 7th Nov
Merch Direction | 28 | Budget handover - 28 days | 2025-07-10: 9th Dec - 17th Dec
Vendor Week
|  |  | Hit 1 Laydown |  |  |  |  | Hit 2 Laydown |  |  |  | Hit 3 Laydown |  |  |  | Hit 4 Laydown |  |  |  |  | Hit 5 Laydown |  |  |  | Hit 6 Laydown
Range build | 30 | Techpack handover - 42 days | 2025-01-06 | 2025-01-09 | 2025-01-16 | 2025-01-23 | 2025-01-30 | 2025-02-06 | 2025-02-13 | 2025-02-20 | 2025-02-27 | 2025-03-06 | 2025-03-13 | 2025-03-20 | 2025-03-27 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26
Tech Pack Handover | 24 | Pre-Laydown - 24 days | 2025-02-05 | 2025-02-08 | 2025-02-15 | 2025-02-22 | 2025-03-01 | 2025-03-08 | 2025-03-15 | 2025-03-22 | 2025-03-29 | 2025-04-05 | 2025-04-12 | 2025-04-19 | 2025-04-26 | 2025-05-03 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26
Planning budget handover | 7 | Pre-Laydown - 7 days | 2025-02-22 | 2025-02-25 | 2025-03-04 | 2025-03-11 | 2025-03-18 | 2025-03-25 | 2025-04-01 | 2025-04-08 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12
Pre Laydown | 7 | Laydown - 7 days | 2025-03-01 | 2025-03-04 | 2025-03-11 | 2025-03-18 | 2025-03-25 | 2025-04-01 | 2025-04-08 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19
Laydown | 7 | Supplier Commitment - 7 days | 2025-03-08 | 2025-03-11 | 2025-03-18 | 2025-03-25 | 2025-04-01 | 2025-04-08 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26
Supplier Commitment Date via Buying Notes + Briefing | 60 | Laydown + 7 days | 2025-03-15 | 2025-03-18 | 2025-03-25 | 2025-04-01 | 2025-04-08 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02
Distribution Handover by Planners | 14 | Laydown + 14 days | 2025-03-22 | 2025-03-25 | 2025-04-01 | 2025-04-08 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02 | 2025-09-09
PO Upload in OTS + Approval from Finance) | 7 | Distribution planning + 7 days | 2025-03-29 | 2025-04-01 | 2025-04-08 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16
Development Sample Approval | 60 | LSD - 60D | 2025-03-15 | 2025-03-18 | 2025-03-25 | 2025-04-01 | 2025-04-08 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02
PP/GPT Approval | 30 | LSD - 30D | 2025-04-14 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02
TOP Approval | 10 | LSD - 10D | 2025-05-04 | 2025-05-07 | 2025-05-14 | 2025-05-21 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22
ADDITIONAL BUFFER | 5
Shipment start date (Central china/ Turkey/ Cambodia) | 7 | Shipment end date - 7 days | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment end date (Central china/ Turkey/ Cambodia) | 45 | RDC GRN - shipment lead time | 2025-05-14 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01
Shipment start date (North China) | 7 | Shipment end date - 7 days | 2025-04-30 | 2025-05-03 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18
Shipment end date (North China) | 52 | RDC GRN - shipment lead time | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment start date (Bangladesh) | 7 | Shipment end date - 7 days | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment end date (Bangladesh) | 45 | RDC GRN - shipment lead time | 2025-05-14 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01
Shipment start date (India,Pakistan, SL) | 7 | Shipment end date - 7 days | 2025-05-19 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-30 | 2025-11-06
Shipment end date (India, Pakistan, SL) | 33 | RDC GRN - shipment lead time | 2025-05-26 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-11-06 | 2025-11-13
Shipment start date ( Indonesia, Vietnam, Thailand) | 7 | Shipment end date - 7 days | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment end date ( Indonesia, Vietnam, Thailand) | 45 | RDC GRN - shipment lead time | 2025-05-14 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01
RDC GRN DATE | 7 |  | 2025-07-03 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21
Launch Date | 0 |  | 2025-07-10 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28
Additional days for Ramadan | 3
| 185 | #REF! | 2025-07-10: 185; 2025-07-20: 185; 2025-08-10: 185; 2025-08-24: 185; 2025-09-07: 185; 2025-09-21: 185; 2025-10-05: 185; 2025-10-19: 185; 2025-11-09: 185; 2025-11-23: 185; 2025-12-07: 185; 2025-12-21: 185
28D production buffer due to CNY impact

## REGULAR CP_45D
REGULAR CRITICAL PATH
EVENTS
WHITE WEDNESDAY SALE
MONTHS |  |  | JUL'25 |  |  |  |  | AUG'25 |  |  |  | SEP'25 |  |  |  | OCT'25 |  |  |  |  | NOV'25 |  |  |  | DEC'25
HIT |  |  | WN25 - HIT 1 |  |  |  |  | WN25 - HIT 2 |  |  |  | WN25 - HIT 3 |  |  |  | WN25 - HIT 4 |  |  |  |  | WN25 - HIT 5 |  |  |  | SS26 HIT 1
GRN WK Considering 7D |  |  | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26
GRN WK Considering 10D for Ramadan (Follow this for Jan /Feb / Mar)
GRN DATE |  |  | 2025-07-03 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21
Launch Sequence |  |  | 2025-07-03: Launch 1; 2025-07-13: Launch 2; 2025-08-03: Launch 1; 2025-08-17: Launch 2; 2025-08-31: Launch 1; 2025-09-14: Launch 2; 2025-09-28: Launch 1; 2025-10-12: Launch 2; 2025-11-02: Launch 1; 2025-11-16: Launch 2; 2025-11-30: Launch 1; 2025-12-14: Launch 2
LAUNCH WK |  |  | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27
LAUNCH DATE |  |  | 2025-07-10 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28
Milestone | Duration | Calculation Guideline
Trend Presentation | 21 | Range Build - 21 days | 2025-07-10: 1st Nov - 7th Nov
Merch Direction | 28 | Budget handover - 28 days | 2025-07-10: 9th Dec - 17th Dec
Vendor Week
|  |  | Hit 1 Laydown |  |  |  |  | Hit 2 Laydown |  |  |  | Hit 3 Laydown |  |  |  | Hit 4 Laydown |  |  |  |  | Hit 5 Laydown |  |  |  | Hit 6 Laydown
Range build | 30 | Techpack handover - 42 days | 2025-01-21 | 2025-01-24 | 2025-01-31 | 2025-02-07 | 2025-02-14 | 2025-02-21 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-04-04 | 2025-04-11 | 2025-04-18 | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11
Tech Pack Handover | 24 | Pre-Laydown - 24 days | 2025-02-20 | 2025-02-23 | 2025-03-02 | 2025-03-09 | 2025-03-16 | 2025-03-23 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-20 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-08 | 2025-06-15 | 2025-06-22 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10
Planning budget handover | 7 | Pre-Laydown - 7 days | 2025-03-09 | 2025-03-12 | 2025-03-19 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-16 | 2025-04-23 | 2025-04-30 | 2025-05-07 | 2025-05-14 | 2025-05-21 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27
Pre Laydown | 7 | Laydown - 7 days | 2025-03-16 | 2025-03-19 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-16 | 2025-04-23 | 2025-04-30 | 2025-05-07 | 2025-05-14 | 2025-05-21 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03
Laydown | 7 | Supplier Commitment - 7 days | 2025-03-23 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-16 | 2025-04-23 | 2025-04-30 | 2025-05-07 | 2025-05-14 | 2025-05-21 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-10
Supplier Commitment Date via Buying Notes + Briefing | 45 | Laydown + 7 days | 2025-03-30 | 2025-04-02 | 2025-04-09 | 2025-04-16 | 2025-04-23 | 2025-04-30 | 2025-05-07 | 2025-05-14 | 2025-05-21 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-17
Distribution Handover by Planners | 14 | Laydown + 14 days | 2025-04-06 | 2025-04-09 | 2025-04-16 | 2025-04-23 | 2025-04-30 | 2025-05-07 | 2025-05-14 | 2025-05-21 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-24
PO Upload in OTS + Approval from Finance) | 7 | Distribution planning + 7 days | 2025-04-13 | 2025-04-16 | 2025-04-23 | 2025-04-30 | 2025-05-07 | 2025-05-14 | 2025-05-21 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-10-01
Development Sample Approval | 60 | LSD - 60D | 2025-03-15 | 2025-03-18 | 2025-03-25 | 2025-04-01 | 2025-04-08 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02
PP/GPT Approval | 30 | LSD - 30D | 2025-04-14 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02
TOP Approval | 10 | LSD - 10D | 2025-05-04 | 2025-05-07 | 2025-05-14 | 2025-05-21 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22
ADDITIONAL BUFFER | 5
Shipment start date (Central china/ Turkey/ Cambodia) | 7 | Shipment end date - 7 days | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment end date (Central china/ Turkey/ Cambodia) | 45 | RDC GRN - shipment lead time | 2025-05-14 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01
Shipment start date (North China) | 7 | Shipment end date - 7 days | 2025-04-30 | 2025-05-03 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18
Shipment end date (North China) | 52 | RDC GRN - shipment lead time | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment start date (Bangladesh) | 7 | Shipment end date - 7 days | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment end date (Bangladesh) | 45 | RDC GRN - shipment lead time | 2025-05-14 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01
Shipment start date (India,Pakistan, SL) | 7 | Shipment end date - 7 days | 2025-05-19 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-30 | 2025-11-06
Shipment end date (India, Pakistan, SL) | 33 | RDC GRN - shipment lead time | 2025-05-26 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-11-06 | 2025-11-13
Shipment start date ( Indonesia, Vietnam, Thailand) | 7 | Shipment end date - 7 days | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment end date ( Indonesia, Vietnam, Thailand) | 45 | RDC GRN - shipment lead time | 2025-05-14 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01
RDC GRN DATE | 7 |  | 2025-07-03 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21
Launch Date | 0 |  | 2025-07-10 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28
Additional days for Ramadan | 3
| 170 | #REF! | 2025-07-10: 170; 2025-07-20: 170; 2025-08-10: 170; 2025-08-24: 170; 2025-09-07: 170; 2025-09-21: 170; 2025-10-05: 170; 2025-10-19: 170; 2025-11-09: 170; 2025-11-23: 170; 2025-12-07: 170; 2025-12-21: 170
28D production buffer due to CNY impact

## REGULAR CP_30D
REGULAR CRITICAL PATH
EVENTS
WHITE WEDNESDAY SALE
MONTHS |  |  | JUL'25 |  |  |  |  | AUG'25 |  |  |  | SEP'25 |  |  |  | OCT'25 |  |  |  |  | NOV'25 |  |  |  | DEC'25
HIT |  |  | WN25 - HIT 1 |  |  |  |  | WN25 - HIT 2 |  |  |  | WN25 - HIT 3 |  |  |  | WN25 - HIT 4 |  |  |  |  | WN25 - HIT 5 |  |  |  | SS26 HIT 1
GRN WK Considering 7D |  |  | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26
GRN WK Considering 10D for Ramadan (Follow this for Jan /Feb / Mar)
GRN DATE |  |  | 2025-07-03 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21
Launch Sequence |  |  | 2025-07-03: Launch 1; 2025-07-13: Launch 2; 2025-08-03: Launch 1; 2025-08-17: Launch 2; 2025-08-31: Launch 1; 2025-09-14: Launch 2; 2025-09-28: Launch 1; 2025-10-12: Launch 2; 2025-11-02: Launch 1; 2025-11-16: Launch 2; 2025-11-30: Launch 1; 2025-12-14: Launch 2
LAUNCH WK |  |  | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27
LAUNCH DATE |  |  | 2025-07-10 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28
Milestone | Duration | Calculation Guideline
Trend Presentation | 21 | Range Build - 21 days | 2025-07-10: 1st Nov - 7th Nov
Merch Direction | 28 | Budget handover - 28 days | 2025-07-10: 9th Dec - 17th Dec
Vendor Week
|  |  | Hit 1 Laydown |  |  |  |  | Hit 2 Laydown |  |  |  | Hit 3 Laydown |  |  |  | Hit 4 Laydown |  |  |  |  | Hit 5 Laydown |  |  |  | Hit 6 Laydown
Range build | 30 | Techpack handover - 42 days | 2025-02-05 | 2025-02-08 | 2025-02-15 | 2025-02-22 | 2025-03-01 | 2025-03-08 | 2025-03-15 | 2025-03-22 | 2025-03-29 | 2025-04-05 | 2025-04-12 | 2025-04-19 | 2025-04-26 | 2025-05-03 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26
Tech Pack Handover | 24 | Pre-Laydown - 24 days | 2025-03-07 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-28 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25
Planning budget handover | 7 | Pre-Laydown - 7 days | 2025-03-24 | 2025-03-27 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11
Pre Laydown | 7 | Laydown - 7 days | 2025-03-31 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18
Laydown | 7 | Supplier Commitment - 7 days | 2025-04-07 | 2025-04-10 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25
Supplier Commitment Date via Buying Notes + Briefing | 30 | Laydown + 7 days | 2025-04-14 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02
Distribution Handover by Planners | 14 | Laydown + 14 days | 2025-04-21 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09
PO Upload in OTS + Approval from Finance) | 7 | Distribution planning + 7 days | 2025-04-28 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16
Development Sample Approval | 60 | LSD - 60D | 2025-03-15 | 2025-03-18 | 2025-03-25 | 2025-04-01 | 2025-04-08 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02
PP/GPT Approval | 30 | LSD - 30D | 2025-04-14 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02
TOP Approval | 10 | LSD - 10D | 2025-05-04 | 2025-05-07 | 2025-05-14 | 2025-05-21 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22
ADDITIONAL BUFFER | 5
Shipment start date (Central china/ Turkey/ Cambodia) | 7 | Shipment end date - 7 days | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment end date (Central china/ Turkey/ Cambodia) | 45 | RDC GRN - shipment lead time | 2025-05-14 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01
Shipment start date (North China) | 7 | Shipment end date - 7 days | 2025-04-30 | 2025-05-03 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18
Shipment end date (North China) | 52 | RDC GRN - shipment lead time | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment start date (Bangladesh) | 7 | Shipment end date - 7 days | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment end date (Bangladesh) | 45 | RDC GRN - shipment lead time | 2025-05-14 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01
Shipment start date (India,Pakistan, SL) | 7 | Shipment end date - 7 days | 2025-05-19 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-30 | 2025-11-06
Shipment end date (India, Pakistan, SL) | 33 | RDC GRN - shipment lead time | 2025-05-26 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-11-06 | 2025-11-13
Shipment start date ( Indonesia, Vietnam, Thailand) | 7 | Shipment end date - 7 days | 2025-05-07 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25
Shipment end date ( Indonesia, Vietnam, Thailand) | 45 | RDC GRN - shipment lead time | 2025-05-14 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01
RDC GRN DATE | 7 |  | 2025-07-03 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21
Launch Date | 0 |  | 2025-07-10 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28
Additional days for Ramadan | 3
| 155 | #REF! | 2025-07-10: 155; 2025-07-20: 155; 2025-08-10: 155; 2025-08-24: 155; 2025-09-07: 155; 2025-09-21: 155; 2025-10-05: 155; 2025-10-19: 155; 2025-11-09: 155; 2025-11-23: 155; 2025-12-07: 155; 2025-12-21: 155
28D production buffer due to CNY impact

## QR_75D
REGULAR CRITICAL PATH
[14 empty] | CNY + FACTORY CLOSURE DATES 2025 |  |  |  | RAMADAN DATES 2025
[12 empty] | PRE-RAMADAN LAUNCH |  |  | RAMADAN LAUNCHES | [14 empty] | 2nd EID LAUNCH
MONTHS |  |  | NOV'24 |  |  |  | DEC'24 |  |  |  | JAN'25 |  |  |  |  | FEB'25 |  |  |  | MAR'25 |  |  |  | APR'25 |  |  |  |  | MAY'25 |  |  |  | JUN'25 |  |  |  | JUL'25 |  |  |  |  | AUG'25 |  |  |  | SEP'25 |  |  |  | OCT'25 |  |  |  |  | NOV'25 |  |  |  | DEC'25
HIT |  |  | WN24 - HIT 5 |  |  |  | SS25 - HIT 1 |  |  |  | SS25 - HIT 2 |  |  |  | SS25 - HIT 3 DROP 1 | SS25 - HIT 3 DROP 2 |  |  | SS25 - HIT 4 DROP 1 | SS25 - HIT 4 DROP2 |  |  |  | SS25 - HIT 5 |  |  |  |  | SS25 - HIT 6 |  |  |  | SS25 - HIT 7 |  |  |  | WN25 - HIT 1 |  |  |  |  | WN25 - HIT 2 |  |  |  | WN25 - HIT 3 |  |  |  | WN25 - HIT 4 |  |  |  |  | WN25 - HIT 5 |  |  |  | SS26 HIT 1
GRN WK Considering 7D (Non-Ramadan Period) | [6 empty] | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52 | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26
GRN WK Considering 10D for Ramadan (Follow this for Jan /Feb / Mar) | [10 empty] | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38
GRN DATE | time axis 2024-11-03 to 2025-12-21
Launch Sequence |  |  | 2024-11-03: Launch 1; 2024-11-17: Launch 2; 2024-12-01: Launch 1; 2024-12-15: Launch 2; 2025-01-02: Launch 1; 2025-01-23: Launch 1; 2025-02-06: Launch 2; 2025-02-20: Launch 1; 2025-03-06: Launch 2; 2025-03-30: Launch 1; 2025-04-13: Launch 2; 2025-05-04: Launch 1; 2025-05-18: Launch 2; 2025-06-01: Launch 1; 2025-06-15: Launch 2; 2025-07-03: Launch 1; 2025-07-13: Launch 2; 2025-08-03: Launch 1; 2025-08-17: Launch 2; 2025-08-31: Launch 1; 2025-09-14: Launch 2; 2025-09-28: Launch 1; 2025-10-12: Launch 2; 2025-11-02: Launch 1; 2025-11-16: Launch 2; 2025-11-30: Launch 1; 2025-12-14: Launch 2
LAUNCH WK |  |  | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52 | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK26
LAUNCH DATE | time axis 2024-11-10 to 2025-12-28
Milestone | Duration | Calculation Guideline
Trend Presentation | 21 | Range Build - 21 days | 2024-12-08: 1st May - 10th May; 2025-07-10: 1st Nov - 7th Nov
Merch Direction | 28 | Budget handover - 28 days | 2024-12-08: 3rd June - 7th June; 2025-07-10: 9th Dec - 17th Dec
Vendor Week | bar: 2024-12-08 to 2024-12-15
[7 empty] | June' 25 | [25 empty] | Hit 7 Laydown |  |  |  | Hit 1 Laydown |  |  |  |  | Hit 2 Laydown |  |  |  | Hit 3 Laydown |  |  |  | Hit 4 Laydown |  |  |  |  | Hit 5 Laydown |  |  |  | Hit 1 Laydown
Range build | 2 | Techpack handover - 2 days | #REF! | #REF! | #REF! | #REF! | 2024-08-29 | 2024-09-05 | 2024-09-12 | 2024-09-19 | 2024-09-23 | 2024-09-30 | 2024-10-07 | 2024-10-14 | 2024-10-16 | 2024-10-16 | 2024-10-16 | 2024-10-16 | 2024-10-16 | 2024-10-28 | 2024-11-04 | 2024-11-11 | 2024-11-18 | 2024-11-28 | 2024-12-05 | 2024-12-12 | 2024-12-19 | 2024-12-26 | 2025-01-02 | 2025-02-06 | 2025-02-13 | 2025-02-20 | 2025-02-27 | 2025-03-06 | 2025-03-13 | 2025-03-20 | 2025-03-31 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18
Tech Pack Handover | 8 | Laydown - 8 days | #REF! | #REF! | #REF! | #REF! | 2024-08-31 | 2024-09-07 | 2024-09-14 | 2024-09-21 | 2024-09-25 | 2024-10-02 | 2024-10-09 | 2024-10-16 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2024-10-30 | 2024-11-06 | 2024-11-13 | 2024-11-20 | 2024-11-30 | 2024-12-07 | 2024-12-14 | 2024-12-21 | 2024-12-28 | 2025-01-04 | 2025-02-08 | 2025-02-15 | 2025-02-22 | 2025-03-01 | 2025-03-08 | 2025-03-15 | 2025-03-22 | 2025-04-02 | 2025-04-05 | 2025-04-12 | 2025-04-19 | 2025-04-26 | 2025-05-03 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20
Laydown | 2 | Supplier Commitment - 2 days | #REF! | 2024-10-23 | 2024-10-30 | 2024-11-06 | 2024-09-08 | 2024-09-15 | 2024-09-22 | 2024-09-29 | 2024-10-03 | 2024-10-10 | 2024-10-17 | 2024-10-24 | 2024-10-26 | 2024-10-26 | 2024-10-26 | 2024-10-26 | 2024-10-26 | 2024-11-07 | 2024-11-14 | 2024-11-21 | 2024-11-28 | 2024-12-08 | 2024-12-15 | 2024-12-22 | 2024-12-29 | 2025-01-05 | 2025-01-12 | 2025-02-16 | 2025-02-23 | 2025-03-02 | 2025-03-09 | 2025-03-16 | 2025-03-23 | 2025-03-30 | 2025-04-10 | 2025-04-13 | 2025-04-20 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-08 | 2025-06-15 | 2025-06-22 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28
Supplier Commitment Date via Buying Notes + Briefing | 75 | Laydown + 2 days | #REF! |  |  |  | 2024-09-10 | 2024-09-17 | 2024-09-24 | 2024-10-01 | 2024-10-05 | 2024-10-12 | 2024-10-19 | 2024-10-26 | 2024-10-28 | 2024-10-28 | 2024-10-28 | 2024-10-28 | 2024-10-28 | 2024-11-09 | 2024-11-16 | 2024-11-23 | 2024-11-30 | 2024-12-10 | 2024-12-17 | 2024-12-24 | 2024-12-31 | 2025-01-07 | 2025-01-14 | 2025-02-18 | 2025-02-25 | 2025-03-04 | 2025-03-11 | 2025-03-18 | 2025-03-25 | 2025-04-01 | 2025-04-12 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-09-30
Distribution Handover by Planners | 2 | Laydown + 2 days | #REF! |  |  |  | 2024-09-10 | 2024-09-17 | 2024-09-24 | 2024-10-01 | 2024-10-05 | 2024-10-12 | 2024-10-19 | 2024-10-26 | 2024-10-28 | 2024-10-28 | 2024-10-28 | 2024-10-28 | 2024-10-28 | 2024-11-09 | 2024-11-16 | 2024-11-23 | 2024-11-30 | 2024-12-10 | 2024-12-17 | 2024-12-24 | 2024-12-31 | 2025-01-07 | 2025-01-14 | 2025-02-18 | 2025-02-25 | 2025-03-04 | 2025-03-11 | 2025-03-18 | 2025-03-25 | 2025-04-01 | 2025-04-12 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-09-30
PO Upload in OTS + Approval from Finance) | 2 | Distribution planning + 7 days | 2024-10-18 | 2024-10-25 | 2024-11-01 | 2024-11-08 | 2024-09-12 | 2024-09-19 | 2024-09-26 | 2024-10-03 | 2024-10-07 | 2024-10-14 | 2024-10-21 | 2024-10-28 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-12-02 | 2024-12-12 | 2024-12-19 | 2024-12-26 | 2025-01-02 | 2025-01-09 | 2025-01-16 | 2025-02-20 | 2025-02-27 | 2025-03-06 | 2025-03-13 | 2025-03-20 | 2025-03-27 | 2025-04-03 | 2025-04-14 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02
Shipment start date (All Countries by Air) | 7 | Shipment end date - 7 days | 2024-10-20 | 2024-10-27 | 2024-11-03 | 2024-11-10 | 2024-11-17 | 2024-11-24 | 2024-12-01 | 2024-12-08 | 2024-12-12 | 2024-12-19 | 2024-12-26 | 2025-01-02 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2025-02-13 | 2025-02-20 | 2025-02-27 | 2025-03-06 | 2025-03-16 | 2025-03-23 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-20 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-08 | 2025-06-19 | 2025-06-22 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07
Shipment end date (All Countries by Air) | 7 | RDC GRN - shipment lead time | 2024-10-27 | 2024-11-03 | 2024-11-10 | 2024-11-17 | 2024-11-24 | 2024-12-01 | 2024-12-08 | 2024-12-15 | 2024-12-19 | 2024-12-26 | 2025-01-02 | 2025-01-09 | 2025-01-11 | 2025-01-11 | 2025-01-11 | 2025-01-11 | 2025-01-11 | 2025-02-20 | 2025-02-27 | 2025-03-06 | 2025-03-13 | 2025-03-23 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-20 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-08 | 2025-06-15 | 2025-06-26 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14
RDC GRN DATE | 7 | time axis 2024-11-03 to 2025-12-21
Launch Date | 0 | time axis 2024-11-10 to 2025-12-28
Additional days for Ramadan | 3
| 101 |  | 2024-11-10: #REF!; 2024-11-17: #REF!; 2024-11-24: #REF!; 2024-12-01: #REF!; 2024-12-08: 101; 2024-12-22: 101; 2025-01-05: 104; 2025-01-19: 104; 2025-02-02: 109; 2025-02-09: 116; 2025-02-23: 130; 2025-03-09: 132; 2025-03-23: 132; 2025-04-06: 129; 2025-04-20: 129; 2025-05-11: 129; 2025-05-25: 101; 2025-06-08: 101; 2025-06-22: 101; 2025-07-10: 101; 2025-07-20: 101; 2025-08-10: 101; 2025-08-24: 101; 2025-09-07: 101; 2025-09-21: 101; 2025-10-05: 101; 2025-10-19: 101; 2025-11-09: 101; 2025-11-23: 101; 2025-12-07: 101; 2025-12-21: 101
Note on M6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Because we have taken 10 days for GRN, the GRN date is actually following 2W prior to launch. Launch is now on Sundays and so 10D GRN date goes to 2W earlier - Discuss with Ramesh.
Note on N7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Because we have taken 10 days for GRN, the GRN date is actually following 2W prior to launch. Launch is now on Sundays and so 10D GRN date goes to 2W earlier - Discuss with Ramesh.

## QR_60D
REGULAR CRITICAL PATH
[14 empty] | CNY + FACTORY CLOSURE DATES 2025 |  |  |  | RAMADAN DATES 2025
[12 empty] | PRE-RAMADAN LAUNCH |  |  | RAMADAN LAUNCHES | [14 empty] | 2nd EID LAUNCH
MONTHS |  |  | NOV'24 |  |  |  | DEC'24 |  |  |  | JAN'25 |  |  |  |  | FEB'25 |  |  |  | MAR'25 |  |  |  | APR'25 |  |  |  |  | MAY'25 |  |  |  | JUN'25 |  |  |  | JUL'25 |  |  |  |  | AUG'25 |  |  |  | SEP'25 |  |  |  | OCT'25 |  |  |  |  | NOV'25 |  |  |  | DEC'25
HIT |  |  | WN24 - HIT 5 |  |  |  | SS25 - HIT 1 |  |  |  | SS25 - HIT 2 |  |  |  | SS25 - HIT 3 DROP 1 | SS25 - HIT 3 DROP 2 |  |  | SS25 - HIT 4 DROP 1 | SS25 - HIT 4 DROP2 |  |  |  | SS25 - HIT 5 |  |  |  |  | SS25 - HIT 6 |  |  |  | SS25 - HIT 7 |  |  |  | WN25 - HIT 1 |  |  |  |  | WN25 - HIT 2 |  |  |  | WN25 - HIT 3 |  |  |  | WN25 - HIT 4 |  |  |  |  | WN25 - HIT 5 |  |  |  | SS26 HIT 1
GRN WK Considering 7D (Non-Ramadan Period) | [6 empty] | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52 | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26
GRN WK Considering 10D for Ramadan (Follow this for Jan /Feb / Mar) | [10 empty] | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38
GRN DATE | time axis 2024-11-03 to 2025-12-21
Launch Sequence |  |  | 2024-11-03: Launch 1; 2024-11-17: Launch 2; 2024-12-01: Launch 1; 2024-12-15: Launch 2; 2025-01-02: Launch 1; 2025-01-23: Launch 1; 2025-02-06: Launch 2; 2025-02-20: Launch 1; 2025-03-06: Launch 2; 2025-03-30: Launch 1; 2025-04-13: Launch 2; 2025-05-04: Launch 1; 2025-05-18: Launch 2; 2025-06-01: Launch 1; 2025-06-15: Launch 2; 2025-07-03: Launch 1; 2025-07-13: Launch 2; 2025-08-03: Launch 1; 2025-08-17: Launch 2; 2025-08-31: Launch 1; 2025-09-14: Launch 2; 2025-09-28: Launch 1; 2025-10-12: Launch 2; 2025-11-02: Launch 1; 2025-11-16: Launch 2; 2025-11-30: Launch 1; 2025-12-14: Launch 2
LAUNCH WK |  |  | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52 | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK26
LAUNCH DATE | time axis 2024-11-10 to 2025-12-28
Milestone | Duration | Calculation Guideline
Trend Presentation | 21 | Range Build - 21 days | 2024-12-08: 1st May - 10th May; 2025-07-10: 1st Nov - 7th Nov
Merch Direction | 28 | Budget handover - 28 days | 2024-12-08: 3rd June - 7th June; 2025-07-10: 9th Dec - 17th Dec
Vendor Week | bar: 2024-12-08 to 2024-12-15
[7 empty] | June' 25 | [25 empty] | Hit 7 Laydown |  |  |  | Hit 1 Laydown |  |  |  |  | Hit 2 Laydown |  |  |  | Hit 3 Laydown |  |  |  | Hit 4 Laydown |  |  |  |  | Hit 5 Laydown |  |  |  | Hit 1 Laydown
Range build | 2 | Techpack handover - 2 days | #REF! | #REF! | #REF! | #REF! | 2024-09-13 | 2024-09-20 | 2024-09-27 | 2024-10-04 | 2024-10-08 | 2024-10-15 | 2024-10-22 | 2024-10-29 | 2024-10-31 | 2024-10-31 | 2024-10-31 | 2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-19 | 2024-11-26 | 2024-12-03 | 2024-12-13 | 2024-12-20 | 2024-12-27 | 2025-01-03 | 2025-01-10 | 2025-02-14 | 2025-02-21 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-04-04 | 2025-04-15 | 2025-04-18 | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03
Tech Pack Handover | 8 | Laydown - 8 days | #REF! | #REF! | #REF! | #REF! | 2024-09-15 | 2024-09-22 | 2024-09-29 | 2024-10-06 | 2024-10-10 | 2024-10-17 | 2024-10-24 | 2024-10-31 | 2024-11-02 | 2024-11-02 | 2024-11-02 | 2024-11-02 | 2024-11-02 | 2024-11-14 | 2024-11-21 | 2024-11-28 | 2024-12-05 | 2024-12-15 | 2024-12-22 | 2024-12-29 | 2025-01-05 | 2025-01-12 | 2025-02-16 | 2025-02-23 | 2025-03-02 | 2025-03-09 | 2025-03-16 | 2025-03-23 | 2025-03-30 | 2025-04-06 | 2025-04-17 | 2025-04-20 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-08 | 2025-06-15 | 2025-06-22 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05
Laydown | 2 | Supplier Commitment - 2 days | #REF! | 2024-10-23 | 2024-10-30 | 2024-11-06 | 2024-09-23 | 2024-09-30 | 2024-10-07 | 2024-10-14 | 2024-10-18 | 2024-10-25 | 2024-11-01 | 2024-11-08 | 2024-11-10 | 2024-11-10 | 2024-11-10 | 2024-11-10 | 2024-11-10 | 2024-11-22 | 2024-11-29 | 2024-12-06 | 2024-12-13 | 2024-12-23 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-20 | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-25 | 2025-04-28 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13
Supplier Commitment Date via Buying Notes + Briefing | 60 | Laydown + 2 days | #REF! |  |  |  | 2024-09-25 | 2024-10-02 | 2024-10-09 | 2024-10-16 | 2024-10-20 | 2024-10-27 | 2024-11-03 | 2024-11-10 | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2024-11-24 | 2024-12-01 | 2024-12-08 | 2024-12-15 | 2024-12-25 | 2025-01-01 | 2025-01-08 | 2025-01-15 | 2025-01-22 | 2025-02-26 | 2025-03-05 | 2025-03-12 | 2025-03-19 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-16 | 2025-04-27 | 2025-04-30 | 2025-05-07 | 2025-05-14 | 2025-05-21 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-15
Distribution Handover by Planners | 2 | Laydown + 2 days | #REF! |  |  |  | 2024-09-25 | 2024-10-02 | 2024-10-09 | 2024-10-16 | 2024-10-20 | 2024-10-27 | 2024-11-03 | 2024-11-10 | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2024-11-24 | 2024-12-01 | 2024-12-08 | 2024-12-15 | 2024-12-25 | 2025-01-01 | 2025-01-08 | 2025-01-15 | 2025-01-22 | 2025-02-26 | 2025-03-05 | 2025-03-12 | 2025-03-19 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-16 | 2025-04-27 | 2025-04-30 | 2025-05-07 | 2025-05-14 | 2025-05-21 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-15
PO Upload in OTS + Approval from Finance) | 2 | Distribution planning + 7 days | 2024-10-18 | 2024-10-25 | 2024-11-01 | 2024-11-08 | 2024-09-27 | 2024-10-04 | 2024-10-11 | 2024-10-18 | 2024-10-22 | 2024-10-29 | 2024-11-05 | 2024-11-12 | 2024-11-14 | 2024-11-14 | 2024-11-14 | 2024-11-14 | 2024-11-14 | 2024-11-26 | 2024-12-03 | 2024-12-10 | 2024-12-17 | 2024-12-27 | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-01-24 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-04-04 | 2025-04-11 | 2025-04-18 | 2025-04-29 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-10 | 2025-10-17
Shipment start date (All Countries by Air) | 7 | Shipment end date - 7 days | 2024-10-20 | 2024-10-27 | 2024-11-03 | 2024-11-10 | 2024-11-17 | 2024-11-24 | 2024-12-01 | 2024-12-08 | 2024-12-12 | 2024-12-19 | 2024-12-26 | 2025-01-02 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2025-02-13 | 2025-02-20 | 2025-02-27 | 2025-03-06 | 2025-03-16 | 2025-03-23 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-20 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-08 | 2025-06-19 | 2025-06-22 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07
Shipment end date (All Countries by Air) | 7 | RDC GRN - shipment lead time | 2024-10-27 | 2024-11-03 | 2024-11-10 | 2024-11-17 | 2024-11-24 | 2024-12-01 | 2024-12-08 | 2024-12-15 | 2024-12-19 | 2024-12-26 | 2025-01-02 | 2025-01-09 | 2025-01-11 | 2025-01-11 | 2025-01-11 | 2025-01-11 | 2025-01-11 | 2025-02-20 | 2025-02-27 | 2025-03-06 | 2025-03-13 | 2025-03-23 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-20 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-08 | 2025-06-15 | 2025-06-26 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14
RDC GRN DATE | 7 | time axis 2024-11-03 to 2025-12-21
Launch Date | 0 | time axis 2024-11-10 to 2025-12-28
Additional days for Ramadan | 3
| 86 |  | 2024-11-10: #REF!; 2024-11-17: #REF!; 2024-11-24: #REF!; 2024-12-01: #REF!; 2024-12-08: 86; 2024-12-22: 86; 2025-01-05: 89; 2025-01-19: 89; 2025-02-02: 94; 2025-02-09: 101; 2025-02-23: 115; 2025-03-09: 117; 2025-03-23: 117; 2025-04-06: 114; 2025-04-20: 114; 2025-05-11: 86; 2025-05-25: 86; 2025-06-08: 86; 2025-06-22: 86; 2025-07-10: 86; 2025-07-20: 86; 2025-08-10: 86; 2025-08-24: 86; 2025-09-07: 86; 2025-09-21: 86; 2025-10-05: 86; 2025-10-19: 86; 2025-11-09: 86; 2025-11-23: 86; 2025-12-07: 86; 2025-12-21: 86
Note on M6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Because we have taken 10 days for GRN, the GRN date is actually following 2W prior to launch. Launch is now on Sundays and so 10D GRN date goes to 2W earlier - Discuss with Ramesh.
Note on N7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Because we have taken 10 days for GRN, the GRN date is actually following 2W prior to launch. Launch is now on Sundays and so 10D GRN date goes to 2W earlier - Discuss with Ramesh.

## QR_45D
REGULAR CRITICAL PATH
[14 empty] | CNY + FACTORY CLOSURE DATES 2025 |  |  |  | RAMADAN DATES 2025
[12 empty] | PRE-RAMADAN LAUNCH |  |  | RAMADAN LAUNCHES | [14 empty] | 2nd EID LAUNCH
MONTHS |  |  | NOV'24 |  |  |  | DEC'24 |  |  |  | JAN'25 |  |  |  |  | FEB'25 |  |  |  | MAR'25 |  |  |  | APR'25 |  |  |  |  | MAY'25 |  |  |  | JUN'25 |  |  |  | JUL'25 |  |  |  |  | AUG'25 |  |  |  | SEP'25 |  |  |  | OCT'25 |  |  |  |  | NOV'25 |  |  |  | DEC'25
HIT |  |  | WN24 - HIT 5 |  |  |  | SS25 - HIT 1 |  |  |  | SS25 - HIT 2 |  |  |  | SS25 - HIT 3 DROP 1 | SS25 - HIT 3 DROP 2 |  |  | SS25 - HIT 4 DROP 1 | SS25 - HIT 4 DROP2 |  |  |  | SS25 - HIT 5 |  |  |  |  | SS25 - HIT 6 |  |  |  | SS25 - HIT 7 |  |  |  | WN25 - HIT 1 |  |  |  |  | WN25 - HIT 2 |  |  |  | WN25 - HIT 3 |  |  |  | WN25 - HIT 4 |  |  |  |  | WN25 - HIT 5 |  |  |  | SS26 HIT 1
GRN WK Considering 7D (Non-Ramadan Period) | [6 empty] | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52 | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26
GRN WK Considering 10D for Ramadan (Follow this for Jan /Feb / Mar) | [10 empty] | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38
GRN DATE | time axis 2024-11-03 to 2025-12-21
Launch Sequence |  |  | 2024-11-03: Launch 1; 2024-11-17: Launch 2; 2024-12-01: Launch 1; 2024-12-15: Launch 2; 2025-01-02: Launch 1; 2025-01-23: Launch 1; 2025-02-06: Launch 2; 2025-02-20: Launch 1; 2025-03-06: Launch 2; 2025-03-30: Launch 1; 2025-04-13: Launch 2; 2025-05-04: Launch 1; 2025-05-18: Launch 2; 2025-06-01: Launch 1; 2025-06-15: Launch 2; 2025-07-03: Launch 1; 2025-07-13: Launch 2; 2025-08-03: Launch 1; 2025-08-17: Launch 2; 2025-08-31: Launch 1; 2025-09-14: Launch 2; 2025-09-28: Launch 1; 2025-10-12: Launch 2; 2025-11-02: Launch 1; 2025-11-16: Launch 2; 2025-11-30: Launch 1; 2025-12-14: Launch 2
LAUNCH WK |  |  | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52 | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK26
LAUNCH DATE | time axis 2024-11-10 to 2025-12-28
Milestone | Duration | Calculation Guideline
Trend Presentation | 21 | Range Build - 21 days | 2024-12-08: 1st May - 10th May; 2025-07-10: 1st Nov - 7th Nov
Merch Direction | 28 | Budget handover - 28 days | 2024-12-08: 3rd June - 7th June; 2025-07-10: 9th Dec - 17th Dec
Vendor Week | bar: 2024-12-08 to 2024-12-15
[7 empty] | June' 25 | [25 empty] | Hit 7 Laydown |  |  |  | Hit 1 Laydown |  |  |  |  | Hit 2 Laydown |  |  |  | Hit 3 Laydown |  |  |  | Hit 4 Laydown |  |  |  |  | Hit 5 Laydown |  |  |  | Hit 1 Laydown
Range build | 2 | Techpack handover - 2 days | #REF! | #REF! | #REF! | #REF! | 2024-09-28 | 2024-10-05 | 2024-10-12 | 2024-10-19 | 2024-10-23 | 2024-10-30 | 2024-11-06 | 2024-11-13 | 2024-11-15 | 2024-11-15 | 2024-11-15 | 2024-11-15 | 2024-11-15 | 2024-11-27 | 2024-12-04 | 2024-12-11 | 2024-12-18 | 2024-12-28 | 2025-01-04 | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-03-01 | 2025-03-08 | 2025-03-15 | 2025-03-22 | 2025-03-29 | 2025-04-05 | 2025-04-12 | 2025-04-19 | 2025-04-30 | 2025-05-03 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18
Tech Pack Handover | 8 | Laydown - 8 days | #REF! | #REF! | #REF! | #REF! | 2024-09-30 | 2024-10-07 | 2024-10-14 | 2024-10-21 | 2024-10-25 | 2024-11-01 | 2024-11-08 | 2024-11-15 | 2024-11-17 | 2024-11-17 | 2024-11-17 | 2024-11-17 | 2024-11-17 | 2024-11-29 | 2024-12-06 | 2024-12-13 | 2024-12-20 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-20 | 2025-01-27 | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-05-02 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20
Laydown | 2 | Supplier Commitment - 2 days | #REF! | 2024-10-23 | 2024-10-30 | 2024-11-06 | 2024-10-08 | 2024-10-15 | 2024-10-22 | 2024-10-29 | 2024-11-02 | 2024-11-09 | 2024-11-16 | 2024-11-23 | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-12-07 | 2024-12-14 | 2024-12-21 | 2024-12-28 | 2025-01-07 | 2025-01-14 | 2025-01-21 | 2025-01-28 | 2025-02-04 | 2025-03-11 | 2025-03-18 | 2025-03-25 | 2025-04-01 | 2025-04-08 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-05-10 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-09-30 | 2025-10-07 | 2025-10-14 | 2025-10-21 | 2025-10-28
Supplier Commitment Date via Buying Notes + Briefing | 45 | Laydown + 2 days | #REF! |  |  |  | 2024-10-10 | 2024-10-17 | 2024-10-24 | 2024-10-31 | 2024-11-04 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-30 | 2025-01-09 | 2025-01-16 | 2025-01-23 | 2025-01-30 | 2025-02-06 | 2025-03-13 | 2025-03-20 | 2025-03-27 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-12 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30
Distribution Handover by Planners | 2 | Laydown + 2 days | #REF! |  |  |  | 2024-10-10 | 2024-10-17 | 2024-10-24 | 2024-10-31 | 2024-11-04 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-30 | 2025-01-09 | 2025-01-16 | 2025-01-23 | 2025-01-30 | 2025-02-06 | 2025-03-13 | 2025-03-20 | 2025-03-27 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-12 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30
PO Upload in OTS + Approval from Finance) | 2 | Distribution planning + 7 days | 2024-10-18 | 2024-10-25 | 2024-11-01 | 2024-11-08 | 2024-10-12 | 2024-10-19 | 2024-10-26 | 2024-11-02 | 2024-11-06 | 2024-11-13 | 2024-11-20 | 2024-11-27 | 2024-11-29 | 2024-11-29 | 2024-11-29 | 2024-11-29 | 2024-11-29 | 2024-12-11 | 2024-12-18 | 2024-12-25 | 2025-01-01 | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-02-08 | 2025-03-15 | 2025-03-22 | 2025-03-29 | 2025-04-05 | 2025-04-12 | 2025-04-19 | 2025-04-26 | 2025-05-03 | 2025-05-14 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-10-04 | 2025-10-11 | 2025-10-18 | 2025-10-25 | 2025-11-01
Shipment start date (All Countries by Air) | 7 | Shipment end date - 7 days | 2024-10-20 | 2024-10-27 | 2024-11-03 | 2024-11-10 | 2024-11-17 | 2024-11-24 | 2024-12-01 | 2024-12-08 | 2024-12-12 | 2024-12-19 | 2024-12-26 | 2025-01-02 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2025-02-13 | 2025-02-20 | 2025-02-27 | 2025-03-06 | 2025-03-16 | 2025-03-23 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-20 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-08 | 2025-06-19 | 2025-06-22 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07
Shipment end date (All Countries by Air) | 7 | RDC GRN - shipment lead time | 2024-10-27 | 2024-11-03 | 2024-11-10 | 2024-11-17 | 2024-11-24 | 2024-12-01 | 2024-12-08 | 2024-12-15 | 2024-12-19 | 2024-12-26 | 2025-01-02 | 2025-01-09 | 2025-01-11 | 2025-01-11 | 2025-01-11 | 2025-01-11 | 2025-01-11 | 2025-02-20 | 2025-02-27 | 2025-03-06 | 2025-03-13 | 2025-03-23 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-20 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-08 | 2025-06-15 | 2025-06-26 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14
RDC GRN DATE | 7 | time axis 2024-11-03 to 2025-12-21
Launch Date | 0 | time axis 2024-11-10 to 2025-12-28
Additional days for Ramadan | 3
| 71 |  | 2024-11-10: #REF!; 2024-11-17: #REF!; 2024-11-24: #REF!; 2024-12-01: #REF!; 2024-12-08: 71; 2024-12-22: 71; 2025-01-05: 74; 2025-01-19: 74; 2025-02-02: 79; 2025-02-09: 86; 2025-02-23: 100; 2025-03-09: 102; 2025-03-23: 102; 2025-04-06: 99; 2025-04-20: 99; 2025-05-11: 71; 2025-05-25: 71; 2025-06-08: 71; 2025-06-22: 71; 2025-07-10: 71; 2025-07-20: 71; 2025-08-10: 71; 2025-08-24: 71; 2025-09-07: 71; 2025-09-21: 71; 2025-10-05: 71; 2025-10-19: 71; 2025-11-09: 71; 2025-11-23: 71; 2025-12-07: 71; 2025-12-21: 71
Note on M6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Because we have taken 10 days for GRN, the GRN date is actually following 2W prior to launch. Launch is now on Sundays and so 10D GRN date goes to 2W earlier - Discuss with Ramesh.
Note on N7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Because we have taken 10 days for GRN, the GRN date is actually following 2W prior to launch. Launch is now on Sundays and so 10D GRN date goes to 2W earlier - Discuss with Ramesh.

## QR_30D
REGULAR CRITICAL PATH
[14 empty] | CNY + FACTORY CLOSURE DATES 2025 |  |  |  | RAMADAN DATES 2025
[12 empty] | PRE-RAMADAN LAUNCH |  |  | RAMADAN LAUNCHES | [14 empty] | 2nd EID LAUNCH
MONTHS |  |  | NOV'24 |  |  |  | DEC'24 |  |  |  | JAN'25 |  |  |  |  | FEB'25 |  |  |  | MAR'25 |  |  |  | APR'25 |  |  |  |  | MAY'25 |  |  |  | JUN'25 |  |  |  | JUL'25 |  |  |  |  | AUG'25 |  |  |  | SEP'25 |  |  |  | OCT'25 |  |  |  |  | NOV'25 |  |  |  | DEC'25
HIT |  |  | WN24 - HIT 5 |  |  |  | SS25 - HIT 1 |  |  |  | SS25 - HIT 2 |  |  |  | SS25 - HIT 3 DROP 1 | SS25 - HIT 3 DROP 2 |  |  | SS25 - HIT 4 DROP 1 | SS25 - HIT 4 DROP2 |  |  |  | SS25 - HIT 5 |  |  |  |  | SS25 - HIT 6 |  |  |  | SS25 - HIT 7 |  |  |  | WN25 - HIT 1 |  |  |  |  | WN25 - HIT 2 |  |  |  | WN25 - HIT 3 |  |  |  | WN25 - HIT 4 |  |  |  |  | WN25 - HIT 5 |  |  |  | SS26 HIT 1
GRN WK Considering 7D (Non-Ramadan Period) | [6 empty] | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52 | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26
GRN WK Considering 10D for Ramadan (Follow this for Jan /Feb / Mar) | [10 empty] | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38
GRN DATE | time axis 2024-11-03 to 2025-12-21
Launch Sequence |  |  | 2024-11-03: Launch 1; 2024-11-17: Launch 2; 2024-12-01: Launch 1; 2024-12-15: Launch 2; 2025-01-02: Launch 1; 2025-01-23: Launch 1; 2025-02-06: Launch 2; 2025-02-20: Launch 1; 2025-03-06: Launch 2; 2025-03-30: Launch 1; 2025-04-13: Launch 2; 2025-05-04: Launch 1; 2025-05-18: Launch 2; 2025-06-01: Launch 1; 2025-06-15: Launch 2; 2025-07-03: Launch 1; 2025-07-13: Launch 2; 2025-08-03: Launch 1; 2025-08-17: Launch 2; 2025-08-31: Launch 1; 2025-09-14: Launch 2; 2025-09-28: Launch 1; 2025-10-12: Launch 2; 2025-11-02: Launch 1; 2025-11-16: Launch 2; 2025-11-30: Launch 1; 2025-12-14: Launch 2
LAUNCH WK |  |  | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52 | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK26
LAUNCH DATE | time axis 2024-11-10 to 2025-12-28
Milestone | Duration | Calculation Guideline
Trend Presentation | 21 | Range Build - 21 days | 2024-12-08: 1st May - 10th May; 2025-07-10: 1st Nov - 7th Nov
Merch Direction | 28 | Budget handover - 28 days | 2024-12-08: 3rd June - 7th June; 2025-07-10: 9th Dec - 17th Dec
Vendor Week | bar: 2024-12-08 to 2024-12-15
[7 empty] | June' 25 | [25 empty] | Hit 7 Laydown |  |  |  | Hit 1 Laydown |  |  |  |  | Hit 2 Laydown |  |  |  | Hit 3 Laydown |  |  |  | Hit 4 Laydown |  |  |  |  | Hit 5 Laydown |  |  |  | Hit 1 Laydown
Range build | 2 | Techpack handover - 2 days | #REF! | #REF! | #REF! | #REF! | 2024-10-13 | 2024-10-20 | 2024-10-27 | 2024-11-03 | 2024-11-07 | 2024-11-14 | 2024-11-21 | 2024-11-28 | 2024-11-30 | 2024-11-30 | 2024-11-30 | 2024-11-30 | 2024-11-30 | 2024-12-12 | 2024-12-19 | 2024-12-26 | 2025-01-02 | 2025-01-12 | 2025-01-19 | 2025-01-26 | 2025-02-02 | 2025-02-09 | 2025-03-16 | 2025-03-23 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-20 | 2025-04-27 | 2025-05-04 | 2025-05-15 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-08 | 2025-06-15 | 2025-06-22 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02
Tech Pack Handover | 8 | Laydown - 8 days | #REF! | #REF! | #REF! | #REF! | 2024-10-15 | 2024-10-22 | 2024-10-29 | 2024-11-05 | 2024-11-09 | 2024-11-16 | 2024-11-23 | 2024-11-30 | 2024-12-02 | 2024-12-02 | 2024-12-02 | 2024-12-02 | 2024-12-02 | 2024-12-14 | 2024-12-21 | 2024-12-28 | 2025-01-04 | 2025-01-14 | 2025-01-21 | 2025-01-28 | 2025-02-04 | 2025-02-11 | 2025-03-18 | 2025-03-25 | 2025-04-01 | 2025-04-08 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-05-06 | 2025-05-17 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-09-30 | 2025-10-07 | 2025-10-14 | 2025-10-21 | 2025-10-28 | 2025-11-04
Laydown | 2 | Supplier Commitment - 2 days | #REF! | 2024-10-23 | 2024-10-30 | 2024-11-06 | 2024-10-23 | 2024-10-30 | 2024-11-06 | 2024-11-13 | 2024-11-17 | 2024-11-24 | 2024-12-01 | 2024-12-08 | 2024-12-10 | 2024-12-10 | 2024-12-10 | 2024-12-10 | 2024-12-10 | 2024-12-22 | 2024-12-29 | 2025-01-05 | 2025-01-12 | 2025-01-22 | 2025-01-29 | 2025-02-05 | 2025-02-12 | 2025-02-19 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-16 | 2025-04-23 | 2025-04-30 | 2025-05-07 | 2025-05-14 | 2025-05-25 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-23 | 2025-07-30 | 2025-08-06 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-10-01 | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-29 | 2025-11-05 | 2025-11-12
Supplier Commitment Date via Buying Notes + Briefing | 30 | Laydown + 2 days | #REF! |  |  |  | 2024-10-25 | 2024-11-01 | 2024-11-08 | 2024-11-15 | 2024-11-19 | 2024-11-26 | 2024-12-03 | 2024-12-10 | 2024-12-12 | 2024-12-12 | 2024-12-12 | 2024-12-12 | 2024-12-12 | 2024-12-24 | 2024-12-31 | 2025-01-07 | 2025-01-14 | 2025-01-24 | 2025-01-31 | 2025-02-07 | 2025-02-14 | 2025-02-21 | 2025-03-28 | 2025-04-04 | 2025-04-11 | 2025-04-18 | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-27 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-10 | 2025-10-17 | 2025-10-24 | 2025-10-31 | 2025-11-07 | 2025-11-14
Distribution Handover by Planners | 2 | Laydown + 2 days | #REF! |  |  |  | 2024-10-25 | 2024-11-01 | 2024-11-08 | 2024-11-15 | 2024-11-19 | 2024-11-26 | 2024-12-03 | 2024-12-10 | 2024-12-12 | 2024-12-12 | 2024-12-12 | 2024-12-12 | 2024-12-12 | 2024-12-24 | 2024-12-31 | 2025-01-07 | 2025-01-14 | 2025-01-24 | 2025-01-31 | 2025-02-07 | 2025-02-14 | 2025-02-21 | 2025-03-28 | 2025-04-04 | 2025-04-11 | 2025-04-18 | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-27 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-10 | 2025-10-17 | 2025-10-24 | 2025-10-31 | 2025-11-07 | 2025-11-14
PO Upload in OTS + Approval from Finance) | 2 | Distribution planning + 7 days | 2024-10-18 | 2024-10-25 | 2024-11-01 | 2024-11-08 | 2024-10-27 | 2024-11-03 | 2024-11-10 | 2024-11-17 | 2024-11-21 | 2024-11-28 | 2024-12-05 | 2024-12-12 | 2024-12-14 | 2024-12-14 | 2024-12-14 | 2024-12-14 | 2024-12-14 | 2024-12-26 | 2025-01-02 | 2025-01-09 | 2025-01-16 | 2025-01-26 | 2025-02-02 | 2025-02-09 | 2025-02-16 | 2025-02-23 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-20 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-29 | 2025-06-01 | 2025-06-08 | 2025-06-15 | 2025-06-22 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16
Shipment start date (All Countries by Air) | 7 | Shipment end date - 7 days | 2024-10-20 | 2024-10-27 | 2024-11-03 | 2024-11-10 | 2024-11-17 | 2024-11-24 | 2024-12-01 | 2024-12-08 | 2024-12-12 | 2024-12-19 | 2024-12-26 | 2025-01-02 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2025-02-13 | 2025-02-20 | 2025-02-27 | 2025-03-06 | 2025-03-16 | 2025-03-23 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-20 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-08 | 2025-06-19 | 2025-06-22 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07
Shipment end date (All Countries by Air) | 7 | RDC GRN - shipment lead time | 2024-10-27 | 2024-11-03 | 2024-11-10 | 2024-11-17 | 2024-11-24 | 2024-12-01 | 2024-12-08 | 2024-12-15 | 2024-12-19 | 2024-12-26 | 2025-01-02 | 2025-01-09 | 2025-01-11 | 2025-01-11 | 2025-01-11 | 2025-01-11 | 2025-01-11 | 2025-02-20 | 2025-02-27 | 2025-03-06 | 2025-03-13 | 2025-03-23 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-20 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-08 | 2025-06-15 | 2025-06-26 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14
RDC GRN DATE | 7 | time axis 2024-11-03 to 2025-12-21
Launch Date | 0 | time axis 2024-11-10 to 2025-12-28
Additional days for Ramadan | 3
| 56 |  | 2024-11-10: #REF!; 2024-11-17: #REF!; 2024-11-24: #REF!; 2024-12-01: #REF!; 2024-12-08: 56; 2024-12-22: 56; 2025-01-05: 59; 2025-01-19: 59; 2025-02-02: 64; 2025-02-09: 71; 2025-02-23: 85; 2025-03-09: 87; 2025-03-23: 87; 2025-04-06: 84; 2025-04-20: 84; 2025-05-11: 56; 2025-05-25: 56; 2025-06-08: 56; 2025-06-22: 56; 2025-07-10: 56; 2025-07-20: 56; 2025-08-10: 56; 2025-08-24: 56; 2025-09-07: 56; 2025-09-21: 56; 2025-10-05: 56; 2025-10-19: 56; 2025-11-09: 56; 2025-11-23: 56; 2025-12-07: 56; 2025-12-21: 56
Note on M6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Because we have taken 10 days for GRN, the GRN date is actually following 2W prior to launch. Launch is now on Sundays and so 10D GRN date goes to 2W earlier - Discuss with Ramesh.
Note on N7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Because we have taken 10 days for GRN, the GRN date is actually following 2W prior to launch. Launch is now on Sundays and so 10D GRN date goes to 2W earlier - Discuss with Ramesh.